## Acceptance AGING
PMOwner | BOONCHOT BORIWUT
STATUS WORK | (Multiple Items)
Row Labels | Sum of ESTIMATE FINAL INCOME | Sum of Accaptance AC#1 AMOUNT | Average of AGING#1 | Sum of Accaptance AC#2 AMOUNT | Average of AGING#2 | Sum of SUM AMOUT | Sum of REMAIN
HAE | 2100030 | 760186.6 | 8.6222 | 172915.2 | -3132.9091 | 933101.8 | 1086574.2
MBB | 2100030 | 760186.6 | 8.6222 | 172915.2 | -3132.9091 | 933101.8 | 1086574.2
TME | 345733.4 | 186341.52 | 17.8533 | 2364 | 49 | 188705.52 | 56286.88
IPRAN | 225486.4 | 186341.52 | 17.8533 | 2364 | 49 | 188705.52 | 36780.88
MBB | 115140 | 0 |  | 0 |  | 0 | 19506
BATERRY | 5107
TRE | 0 | 0 |  | 0 |  | 0 | 0
DISMANTLE | 0 | 0 |  | 0 |  | 0 | 0
Grand Total | 2445763.4 | 946528.12 | 12.8182 | 175279.2 | -2929.8085 | 1121807.32 | 1142861.08
PMOwner | BOONCHOT BORIWUT
STATUS WORK | COMPLETED
Row Labels | Sum of ESTIMATE FINAL INCOME | Sum of Accaptance AC#1 AMOUNT | Average of AGING#1 | Sum of Accaptance AC#2 AMOUNT | Average of AGING#2 | Sum of SUM AMOUT | Sum of REMAIN
HAE | 1325040 | 760186.6 | 15.2157 | 172915.2 | -5626.449 | 933101.8 | 391938.2
MBB | 1325040 | 760186.6 | 15.2157 | 172915.2 | -5626.449 | 933101.8 | 391938.2
TME | 244992.4 | 186341.52 | 17.8533 | 2364 | 49 | 188705.52 | 56286.88
IPRAN | 225486.4 | 186341.52 | 17.8533 | 2364 | 49 | 188705.52 | 36780.88
MBB | 19506 | 0 |  | 0 |  | 0 | 19506
TRE | 0 | 0 |  | 0 |  | 0 | 0
DISMANTLE | 0 | 0 |  | 0 |  | 0 | 0
Grand Total | 1570032.4 | 946528.12 | 16.7857 | 175279.2 | -5007.3091 | 1121807.32 | 448225.08

## Milestore AGING
SQC Milestone
PMOwner | BOONCHOT BORIWUT
Row Labels | Average of AGING 1st Milestone
HAE | 1.8504
CANCEL
CANCEL
MBB | 1.8504
Adisak Chanmao | 3.4762
Palagon Prommueangma | 1.7778
(blank) | 0
TME | -542.9765
CANCEL
CANCEL
IPRAN | 0.50649
Adisak Chanmao | 0.50649
MBB | -6598.8571
Adisak Chanmao | 0
Palagon Prommueangma | -46192
(blank) | 0
BATERRY | 0
(blank) | 0
Grand Total | -216.5943
OWNER DOC
PMOwner | BOONCHOT BORIWUT
Row Labels | Average of AGING 2nd Milestone
HAE | -1473.856
CANCEL
CANCEL
MBB | -1473.856
Adisak Chanmao | 7.5
Apichart kampuang | 7.15
น.ส. หทัยรัตน์ สิงห์แก้ว | 8.3659
(blank) | -2979.5645
TME | -548.5854
CANCEL
Adisak Chanmao
IPRAN | 16.1067
Adisak Chanmao | 20.32
Sermsiri Bampentam | 14
MBB | -7698.6667
Adisak Chanmao
(blank) | -7698.6667
BATERRY | 0
(blank) | 0
Grand Total | -1107.3237

## DOC AGING (hidden)
OWNER DOC
PMOwner | BOONCHOT BORIWUT
Row Labels | Average of AGING 2nd Milestone
HAE | -1473.856
CANCEL
CANCEL
MBB | -1473.856
Adisak Chanmao | 7.5
Apichart kampuang | 7.15
น.ส. หทัยรัตน์ สิงห์แก้ว | 8.3659
(blank) | -2979.5645
TME | -548.5854
CANCEL
Adisak Chanmao
IPRAN | 16.1067
Adisak Chanmao | 20.32
Sermsiri Bampentam | 14
MBB | -7698.6667
Adisak Chanmao
(blank) | -7698.6667
BATERRY | 0
(blank) | 0
Grand Total | -1107.3237

## 2026
PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM |  | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | CPO | ACCOUNT | ACCOUNT | PM | PM | PM | PM | CPO | CPO | CPO | CPO
270 | 279 | 279 | 2853084.94 | 3489253.4 | 272 | 279 | 279 | 279 | 279 | 279 | 216 | 216 |  | 217 | 217 | 217 | 218 | 210 | 277 | 103719 | 2410381.4 | 201476 | 412792 | 3128368.4 | 58250 | 176 | 3186618.4 | 2435974.3263 | 856814.52 | 843614.52 | 13200 | 0 | 173 | 167 | 110 | 793 | 1884942.4 | 470165.6 | 17493.6 | 487659.2 | 665675.5 | 669877.7 | 1735926.12 | 635296.62 | 140721.3 | 213 | 181 | 214 | 529 | 7448.16 |  | 0
WON CODE | WON NAME | SITE/DUID | Estimate Plan | Estimate income | Period WON | Project | Phase | Site | PMOwner | Region | Installation | On-Service | MONTH | Subcon | Subcon Account | TYPE SUB | PE Owner | DOC Owner | WK NUM | SO Survey | SO Service | SO Material | SO Logistics | SUM SO | ADDITIONAL WORK | VO Submit Date | ESTIMATE FINAL INCOME | DLPlan | DLPRPO | SERVICE | DOC | OTHER | DL END Y/N/OTHER | PR END Y/N | PO END Y/N | CREDIT NOTE | SO GGD | SO AC1 | SO AC2 | SO SAP | PR SUM | PO APPROVED | AR | AP | GR INHOUSE | 1st Milestone | 2nd Milestone | 3rd Milestone | ACCRUE REV | ACCRUE DL | CUSTOMER | CHECK | REMARK | SAP CODE | AGING 1st Milestone | AGING 2nd Milestone | STATUS WORK | WORK TYPE | Accaptance AC#1 AMOUNT | Accaptance AC#1 DONE | AGING#1 | Accaptance AC#2 AMOUNT | Accaptance AC#2 DONE | AGING#2 | SUM AMOUT | REMAIN
29739 | HAS-CC_Q425-BCHFG | BCHFG_2025 Capacity Expansion Ph7_EXP_SR | 14571.2 | 18214 | 2025-12-01 | HAS | CC_Q425 | BCHFG | NATTAWOOT SUWAN | SR | 2026-01-05 | 2026-01-05 | 2026-01-05 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK2 | 0 | 11472 | 2579 | 4163 | 18214 | 0 | - | 18214 | 14571.2 | 14571.2 | 14571.2 | 0 | 0 | Y | Y | Y |  | 19007 | 14772.4 | 3441.6 | 18214 | 14571.2 | 14571.2 | 19007 | 14571.2 | 0 | 2026-01-05 | 2026-01-06 | - | 0 | 0 | HUAWEI | [7 empty] | 15327.5 | 2026-01-16 | 11 | 3679.5 | 2026-02-08 | 34 | 19007 | -793
29498 | HAS-CC_Q325-KSPMT | KSPMT_2025_Promote Node B_SR | 5336.3 | 6278 | 2025-10-01 | HAS | CC_Q325 | KSPMT | NATTAWOOT SUWAN | SR | 2026-01-05 | 2026-01-05 | 2026-01-05 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK2 | 0 | 5287 | 0 | 991 | 6278 | 0 | - | 6278 | 5336.3 | 4599.2 | 4599.2 | 0 | 0 | Y | Y | Y |  | 6278 | 0 | 0 | 0 | 4599.2 | 4599.2 | 5749 | 3457.28 | 0 | 2026-03-23 | 2026-03-23 | - | 529 | 1141.92 | HUAWEI | [7 empty] | 4321.6 | 2026-03-29 | 83 | 1427.4 | 2026-04-30 | 115 | 5749 | 529
29738 | HAS-CC_Q425-ANBTK | ANBTK_2025 Capacity Expansion Ph7_EXP_SR | 14571.2 | 18214 | 2025-12-01 | HAS | CC_Q425 | ANBTK | NATTAWOOT SUWAN | SR | 2026-01-06 | 2026-01-06 | 2026-01-06 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK2 | 0 | 11472 | 2579 | 4163 | 18214 | 0 | - | 18214 | 14571.2 | 14571.2 | 14571.2 | 0 | 0 | Y | Y | Y |  | 19007 | 14772.4 | 3441.6 | 18214 | 14571.2 | 14571.2 | 19007 | 14571.2 | 0 | 2026-01-12 | 2026-01-08 | - | 0 | 0 | HUAWEI | [7 empty] | 15327.5 | 2026-02-02 | 27 | 3679.5 | 2026-02-08 | 33 | 19007 | -793
29690 | HAS-CC_Q425-NWKSK | NWKSK_2025 Coverage Expansion Ph2_New_SR | 27696 | 34620 | 2025-12-01 | HAS | CC_Q425 | NWKSK | NATTAWOOT SUWAN | SR | 2026-01-07 | 2026-01-07 | 2026-01-07 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK2 | 0 | 26885 | 5158 | 2577 | 34620 | 0 | - | 34620 | 27696 | 27272.8 | 27272.8 | 0 | 0 | Y | Y | Y |  | 34620 | 26554.5 | 0 | 26554.5 | 27272.8 | 27272.8 | 34620 | 27272.8 | 0 | 2026-01-07 | 2026-02-04 | - | 0 | 0 | HUAWEI | [7 empty] | 26554.5 | 2026-01-16 | 9 | 8065.5 | 2026-02-28 | 52 | 34620 | 0
29685 | HAS-CC_Q425-BSPHS | BSPHS_2025 Coverage Expansion Ph1_New_SR | 27632 | 34540 | 2025-12-01 | HAS | CC_Q425 | BSPHS | NATTAWOOT SUWAN | SR | 2026-01-07 | 2026-01-07 | 2026-01-07 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK2 | 0 | 26805 | 5158 | 2577 | 34540 | 0 | - | 34540 | 27632 | 27208.8 | 27208.8 | 0 | 0 | Y | Y | Y |  | 34540 | 0 | 0 | 0 | 27208.8 | 27208.8 | 34540 | 20902.56 | 0 | 2026-03-15 | 2026-03-17 | - | 0 | 6306.24 | HUAWEI | [7 empty] | 26498.5 | 2026-03-20 | 72 | 8041.5 | 2026-03-29 | 81 | 34540 | 0
29741 | HAS-CC_Q425-MPBST | MPBST_2025 Coverage Expansion Ph1_New_SR | 26839.2 | 33549 | 2025-12-01 | HAS | CC_Q425 | MPBST | NATTAWOOT SUWAN | SR | 2026-01-07 | 2026-01-07 | 2026-01-07 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK2 | 0 | 26805 | 5158 | 1586 | 33549 | 0 | - | 33549 | 26839.2 | 26416 | 26416 | 0 | 0 | Y | Y | Y |  | 33549 | 25507.5 | 8041.5 | 33549 | 26416 | 26416 | 33549 | 26416 | 0 | 2026-01-06 | 2026-01-21 | - | 0 | 0 | HUAWEI | [7 empty] | 25507.5 | 2026-01-16 | 9 | 8041.5 | 2026-02-08 | 32 | 33549 | 0
29768 | HAS-CC_Q126-BHTAG | BHTAG_2025 Coverage Expansion Ph1_New_SR | 19470.1 | 22906 | 2026-01-01 | HAS | CC_Q126 | BHTAG | NATTAWOOT SUWAN | SR | 2026-01-17 | 2026-01-17 | 2026-01-17 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK3 | 0 | 18741 | 2579 | 1586 | 22906 | 0 | - | 22906 | 18324.8 | 18324.8 | 18324.8 | 0 | 0 | Y | Y | Y |  | 22906 | 0 | 0 | 0 | 18324.8 | 18324.8 | 22906 | 18324.8 | 0 | 2026-03-15 | 2026-03-17 | - | 0 | 0 | HUAWEI | [7 empty] | 17283.7 | 2026-03-20 | 62 | 5622.3 | 2026-03-29 | 71 | 22906 | 0
29769 | HAS-CC_Q126-MBTKD | MBTKD_2025 Coverage Expansion Ph1_New_SR | 32382.45 | 38097 | 2026-01-01 | HAS | CC_Q126 | MBTKD | NATTAWOOT SUWAN | SR | 2026-01-16 | 2026-01-16 | 2026-01-16 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK3 | 0 | 31353 | 5158 | 1586 | 38097 | 0 | - | 38097 | 30477.6 | 30054.4 | 30054.4 | 0 | 0 | Y | Y | Y |  | 38097 | 0 | 0 | 0 | 30054.4 | 30054.4 | 38097 | 30054.4 | 0 | 2026-02-28 | 2026-03-04 | - | 0 | 0 | HUAWEI | [7 empty] | 28691.1 | 2026-03-15 | 58 | 9405.9 | 2026-03-20 | 63 | 38097 | 0
29753 | HAE-Cap_Q126-TBKDM | TBKDM_2025 Capacity Expansion Ph8_EXP_ER | 14999.6 | 18293 | 2026-01-01 | HAE | Cap_Q126 | TBKDM | BOONCHOT BORIWUT | ER | 2026-01-19 | 2026-01-19 | 2026-01-19 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 10758 | 2579 | 4163 | 18293 | 0 | - | 18293 | 30477.6 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 18293 | 14272.6 | 0 | 14272.6 | 300 | 300 | 18293 | 300 | 3658.6 | 2026-01-24 | 2026-01-28 | - | 0 | 0 | HUAWEI |  |  |  | 5 | 9 | COMPLETED | MBB | 15065.6 | 2026-02-02 | 14 | 3227.4 | 2026-02-28 | 40 | 18293 | 0
29754 | HAE-Cap_Q126-TLRPM | TLRPM_2025 Capacity Expansion Ph8_EXP_ER | 10631.2 | 12966 | 2026-01-01 | HAE | Cap_Q126 | TLRPM | BOONCHOT BORIWUT | ER | 2026-01-19 | 2026-01-19 | 2026-01-19 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | Adisak Chanmao | 26WK4 | 793 | 8008 | 2579 | 1586 | 12966 | 4453 | 2026-02-23 | 17419 | 30477.6 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 20062 | 9770.6 | 0 | 9770.6 | 300 | 300 | 19533 | 300 | 2593.2 | 2026-01-22 | 2026-01-28 | - | 529 | 0 | HUAWEI |  |  |  | 3 | 9 | COMPLETED | MBB | 16496.4 | 2026-02-02 | 14 | 3036.6 | 2026-02-28 | 40 | 19533 | -2114
29762 | HAE-Cap_Q126-CPCEM | CPCEM_2025 Capacity Expansion Ph8_EXP_ER | 11391.4 | 13892 | 2026-01-01 | HAE | Cap_Q126 | CPCEM | BOONCHOT BORIWUT | ER | 2026-01-17 | 2026-01-17 | 2026-01-17 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK3 | 793 | 8934 | 2579 | 1586 | 13892 | 0 | - | 13892 | 30477.6 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 13892 | 10418.8 | 0 | 10418.8 | 300 | 300 | 13892 | 300 | 2778.4 | 2026-01-17 | 2026-01-21 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 4 | COMPLETED | MBB | 11211.8 | 2026-02-02 | 16 | 2680.2 | 2026-02-28 | 42 | 13892 | 0
29763 | HAE-Cap_Q126-WSNIM | WSNIM_2025 Capacity Expansion Ph8_EXP_ER | 19812.4 | 24162 | 2026-01-01 | HAE | Cap_Q126 | WSNIM | BOONCHOT BORIWUT | ER | 2026-01-16 | 2026-01-16 | 2026-01-16 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK3 | 793 | 16627 | 2579 | 4163 | 24162 | 4453 | 2026-01-29 | 28615 | 30477.6 | 11925 | 11625 | 300 | 0 | Y | Y |  |  | 31258 | 22833.9 | 0 | 22833.9 | 11985 | 11865 | 31258 | 11865 | 0 | 2026-01-17 | 2026-02-12 | - | 0 | 60 | HUAWEI |  |  |  | 1 | 27 | COMPLETED | MBB | 25477 | 2026-02-02 | 17 | 5781 | 2026-03-15 | 58 | 31258 | -2643
29767 | HAE-Cap_Q126-WNALM | WNALM_2025 Capacity Expansion Ph8_EXP_ER | 20809.8 | 25379 | 2026-01-01 | HAE | Cap_Q126 | WNALM | BOONCHOT BORIWUT | ER | 2026-01-19 | 2026-01-19 | 2026-01-19 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 17844 | 2579 | 4163 | 25379 | 792 | 2026-01-29 | 26171 | 30477.6 | 12235 | 11935 | 300 | 0 | Y | Y | Y |  | 26171 | 19787.2 | 0 | 19787.2 | 12235 | 12235 | 26171 | 12235 | 0 | 2026-01-20 | 2026-01-23 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 4 | COMPLETED | MBB | 20580.2 | 2026-02-02 | 14 | 5590.8 | 2026-02-28 | 40 | 26171 | 0
29694 | HAS-CC_Q425-YSMAI | YSMAI_2025 Capacity Expansion Ph6_EXP_SR | 11398.4 | 14248 | 2025-12-01 | HAS | CC_Q425 | YSMAI | NATTAWOOT SUWAN | SR | 2026-01-23 | 2026-01-23 | 2026-01-23 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK4 | 0 | 7506 | 2579 | 4163 | 14248 | 0 | - | 14248 | 11398.4 | 11398.4 | 11398.4 | 0 | 0 | Y | Y | Y |  | 14248 | 11996.2 | 2251.8 | 14248 | 11398.4 | 11398.4 | 14248 | 11398.4 | 0 | 2025-12-26 | 2026-01-06 | - | 0 | 0 | HUAWEI | [7 empty] | 11996.2 |  |  | 2251.8 | 2026-02-08 | 16 | 14248 | 0
29686 | HAS-CC_Q425-LSHPT | LSHPT_2025 Capacity Expansion Ph6_EXP_SR | 12752 | 15940 | 2025-12-01 | HAS | CC_Q425 | LSHPT | NATTAWOOT SUWAN | SR | 2026-01-24 | 2026-01-24 | 2026-01-24 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK4 | 0 | 9198 | 2579 | 4163 | 15940 | 0 | - | 15940 | 12752 | 12752 | 12752 | 0 | 0 | Y | Y | Y |  | 15940 | 13180.6 | 0 | 13180.6 | 12752 | 12752 | 15940 | 12752 | 0 | 2026-02-04 | 2026-01-14 | - | 0 | 0 | HUAWEI | [7 empty] | 13180.6 | 2026-02-14 | 21 | 2759.4 | 2026-03-20 | 55 | 15940 | 0
29740 | HAS-CC_Q425-HNDAN | HNDAN_2025 Coverage Expansion Ph2_New_SR | 21053.6 | 26317 | 2025-12-01 | HAS | CC_Q425 | HNDAN | NATTAWOOT SUWAN | SR | 2026-01-22 | 2026-01-22 | 2026-01-22 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK4 | 0 | 22152 | 2579 | 1586 | 26317 | 0 | - | 26317 | 21053.6 | 21053.6 | 21053.6 | 0 | 0 | Y | Y | Y |  | 26317 | 19671.4 | 0 | 19671.4 | 21053.6 | 21053.6 | 26317 | 21053.6 | 0 | 2025-12-26 | 2026-02-20 | - | 0 | 0 | HUAWEI | [7 empty] | 19671.4 |  |  | 6645.6 | 2026-03-15 | 52 | 26317 | 0
29725 | HAE-Cap_Q425-WHCSM | WHCSM_2024 Coverage Expansion ph.2_New Site-Relocate_ER | 47237.74 | 57607 | 2026-01-01 | HAE | Cap_Q425 | WHCSM | BOONCHOT BORIWUT | ER | 2026-01-21 | 2026-01-23 | 2026-01-23 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 44914 | 7737 | 4163 | 57607 | 0 | - | 57607 | 35716.34 | 22685 | 22385 | 300 | 0 | Y | Y | Y |  | 57607 | 40876.4 | 0 | 40876.4 | 22685 | 22685 | 52955 | 22685 | 0 | 2026-02-10 | 2026-02-15 | - | 4652 | 0 | HUAWEI |  |  |  | 18 | 23 | COMPLETED | MBB | 40876.4 | 2026-02-14 | 22 | 12078.6 | 2026-03-06 | 42 | 52955 | 4652
29757 | HAE-Cap_Q126-TLBIM | TLBIM_2025 Capacity Expansion Ph8_EXP_ER | 15368.6 | 18743 | 2026-01-01 | HAE | Cap_Q126 | TLBIM | BOONCHOT BORIWUT | ER | 2026-01-22 | 2026-01-22 | 2026-01-22 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 11208 | 2579 | 4163 | 18743 | 0 | - | 18743 | 11620.66 | 8040 | 7740 | 300 | 0 | Y | Y | Y |  | 18743 | 14587.6 | 0 | 14587.6 | 8040 | 8040 | 18743 | 8040 | 0 | 2026-01-22 | 2026-01-26 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 4 | COMPLETED | MBB | 15380.6 | 2026-02-02 | 11 | 3362.4 | 2026-02-28 | 37 | 18743 | 0
29758 | HAE-Cap_Q126-KNBPM | KNBPM_2025 Capacity Expansion Ph8_EXP_ER | 22933.8 | 27969 | 2026-01-01 | HAE | Cap_Q126 | KNBPM | BOONCHOT BORIWUT | ER | 2026-01-25 | 2026-01-26 | 2026-01-26 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK5 | 793 | 20434 | 2579 | 4163 | 27969 | 4453 | 2026-02-23 | 32422 | 17340.78 | 13255 | 12955 | 300 | 0 | Y | Y | Y |  | 32422 | 21045.8 | 0 | 21045.8 | 13255 | 13255 | 32422 | 13255 | 0 | 2026-01-29 | 2026-02-04 | - | 0 | 0 | HUAWEI |  |  |  | 3 | 9 | COMPLETED | MBB | 26291.8 | 2026-02-08 | 13 | 6130.2 | 2026-02-28 | 33 | 32422 | 0
29759 | HAE-Cap_Q126-KPWTM | KPWTM_2025 Capacity Expansion Ph8_EXP_ER | 12961.6 | 15808 | 2026-01-01 | HAE | Cap_Q126 | KPWTM | BOONCHOT BORIWUT | ER | 2026-01-26 | 2026-01-26 | 2026-01-26 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK5 | 793 | 8273 | 2579 | 4163 | 15808 | 0 | - | 15808 | 9800.96 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 15808 | 12533.1 | 0 | 12533.1 | 300 | 300 | 15808 | 300 | 3161.6 | 2026-02-04 | 2026-02-07 | - | 0 | 0 | HUAWEI |  |  |  | 9 | 12 | COMPLETED | MBB | 13326.1 | 2026-02-14 | 19 | 2481.9 | 2026-02-28 | 33 | 15808 | 0
29760 | HAE-Cap_Q126-CPTCM | CPTCM_2025 Capacity Expansion Ph8_EXP_ER | 15802.2 | 19271 | 2026-01-01 | HAE | Cap_Q126 | CPTCM | BOONCHOT BORIWUT | ER | 2026-01-24 | 2026-01-24 | 2026-01-24 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 11736 | 2579 | 4163 | 19271 | 4453 | 2026-02-23 | 23724 | 11948.02 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 23724 | 14957.2 | 0 | 14957.2 | 300 | 300 | 23724 | 300 | 3854.2 | 2026-02-03 | 2026-02-10 | - | 0 | 0 | HUAWEI |  |  |  | 10 | 17 | COMPLETED | MBB | 20203.2 | 2026-02-14 | 21 | 3520.8 | 2026-03-15 | 50 | 23724 | 0
29761 | HAE-Cap_Q126-BKWNM | BKWNM_2025 Capacity Expansion Ph8_EXP_ER | 20810.8 | 25379 | 2026-01-01 | HAE | Cap_Q126 | BKWNM | BOONCHOT BORIWUT | ER | 2026-01-24 | 2026-01-24 | 2026-01-24 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 17844 | 2579 | 4163 | 25379 | 0 | - | 25379 | 15734.98 | 11975 | 11675 | 300 | 0 | Y | Y |  |  | 25379 | 19232.8 | 0 | 19232.8 | 11975 | 11975 | 25379 | 11975 | 0 | 2026-01-25 | 2026-01-26 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 2 | COMPLETED | MBB | 20025.8 | 2026-02-02 | 9 | 5353.2 | 2026-02-28 | 35 | 25379 | 0
29764 | HAE-Cap_Q126-TTBPM | TTBPM_2025 Capacity Expansion Ph8_EXP_ER | 23694.2 | 28896 | 2026-01-01 | HAE | Cap_Q126 | TTBPM | BOONCHOT BORIWUT | ER | 2026-01-22 | 2026-01-22 | 2026-01-22 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 21361 | 2579 | 4163 | 28896 | 0 | - | 28896 | 17915.52 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 28896 | 21694.7 | 0 | 21694.7 | 300 | 300 | 28896 | 300 | 5779.2 | 2026-01-22 | 2026-01-24 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 2 | COMPLETED | MBB | 22487.7 | 2026-02-02 | 11 | 6408.3 | 2026-02-28 | 37 | 28896 | 0
29766 | HAE-Cap_Q126-WPNRM | WPNRM_2025 Capacity Expansion Ph8_EXP_ER | 11607.2 | 14156 | 2026-01-01 | HAE | Cap_Q126 | WPNRM | BOONCHOT BORIWUT | ER | 2026-01-22 | 2026-01-22 | 2026-01-22 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK4 | 793 | 9198 | 2579 | 1586 | 14156 | 8906 | 2026-02-23 | 23062 | 8776.72 | 300 | 0 | 300 | 0 | Y | Y |  |  | 23062 | 10603.6 | 0 | 10603.6 | 360 | 240 | 23062 | 240 | 2831.2 | 2026-01-22 | 2026-01-23 | - | 0 | 60 | HUAWEI |  |  |  | 0 | 1 | COMPLETED | MBB | 20302.6 | 2026-02-02 | 11 | 2759.4 | 2026-02-28 | 37 | 23062 | 0
29755 | HAE-Cap_Q126-PNTHM | PNTHM_2025 Capacity Expansion Ph8_EXP_ER | 20744.8 | 25299 | 2026-01-01 | HAE | Cap_Q126 | PNTHM | BOONCHOT BORIWUT | ER | 2026-01-31 | 2026-01-31 | 2026-01-31 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK5 | 793 | 17764 | 2579 | 4163 | 25299 | 4453 | 2026-02-23 | 29752 | 15685.38 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 29752 | 0 | 0 | 0 | 300 | 300 | 29752 | 300 | 5059.8 | 2026-02-10 | 2026-02-19 | - | 0 | 0 | HUAWEI |  |  |  | 10 | 19 | COMPLETED | MBB | 24422.8 | 2026-02-28 | 28 | 5329.2 | 2026-03-15 | 43 | 29752 | 0
29765 | HAE-Cap_Q126-WTWAM | WTWAM_2025 Capacity Expansion Ph8_EXP_ER | 19184.2 | 23396 | 2026-01-01 | HAE | Cap_Q126 | WTWAM | BOONCHOT BORIWUT | ER | 2026-02-02 | 2026-02-02 | 2026-02-02 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 15861 | 2579 | 4163 | 23396 | 0 | - | 23396 | 14505.52 | 11555 | 11255 | 300 | 0 | Y | Y |  |  | 23396 | 17844.7 | 0 | 17844.7 | 11615 | 11495 | 23396 | 11495 | 0 | 2026-02-04 | 2026-02-12 | - | 0 | 60 | HUAWEI |  |  |  | 2 | 10 | COMPLETED | MBB | 18637.7 | 2026-02-14 | 12 | 4758.3 | 2026-03-15 | 41 | 23396 | 0
EP26010018 | HAE-NEWSITE-SHTLM | SHTLM_2024 Coverage Expansion ph.2_New Site-Relocate_ER | 22252.34 | 27137 | 2026-01-01 | HAE | NEWSITE | SHTLM | BOONCHOT BORIWUT | ER | 2026-01-27 | 2026-01-31 | 2026-01-31 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK5 | 793 | 22179 | 2579 | 1586 | 27137 | 5024 | 2026-02-23 | 32161 | 16824.94 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 32161 | 5142.8 | 0 | 5142.8 | 300 | 300 | 5222 | 300 | 5427.4 | 2026-02-06 | 2026-02-10 | - | 26939 | 0 | HUAWEI |  |  |  | 6 | 10 | COMPLETED | MBB | 6622.6 | 2026-02-14 | 14 | 79.2 | 2026-03-06 | 34 | 6701.8 | 25459.2
EP26020021 | TME-DIS_ATN-RYG0118 | RYG0118-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-01 | TME | DIS_ATN | RYG0118 | BOONCHOT BORIWUT | ER | 2026-01-29 | 2026-01-29 | 2026-01-29 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK5 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 1687 | 0 | 1687 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-01-29 | 2026-02-12 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 14 | COMPLETED | IPRAN | 1687 | 2026-02-20 | 22 | 0 |  |  | 1687 | 394
EP26020022 | TME-DIS_ATN-RYG0146 | RYG0146-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-01 | TME | DIS_ATN | RYG0146 | BOONCHOT BORIWUT | ER | 2026-01-29 | 2026-01-29 | 2026-01-29 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK5 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 1687 | 0 | 1687 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-01-29 | 2026-02-20 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 22 | COMPLETED | IPRAN | 1687 | 2026-02-20 | 22 | 0 |  |  | 1687 | 394
EP26020023 | TME-DIS_ATN-RYG0168 | RYG0168-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-01 | TME | DIS_ATN | RYG0168 | BOONCHOT BORIWUT | ER | 2026-01-29 | 2026-01-29 | 2026-01-29 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK5 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-02-20 | - | 394 | 0 | HUAWEI |  |  |  | 20 | 22 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 30 | 0 |  |  | 1687 | 394
EP26020024 | TME-DIS_ATN-RYG0083 | RYG0083-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-01 | TME | DIS_ATN | RYG0083 | BOONCHOT BORIWUT | ER | 2026-01-30 | 2026-01-30 | 2026-01-30 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK5 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 1687 | 0 | 1687 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-01-30 | 2026-02-12 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 13 | COMPLETED | IPRAN | 1687 | 2026-02-20 | 21 | 0 |  |  | 1687 | 394
EP26020025 | TME-REPIPRAN-TRT0164 | TRT0164_TRT3001_D_Retain_New_EAST_R3 | 2736.06 | 7468 | 2026-02-01 | TME | REPIPRAN | TRT0164 | BOONCHOT BORIWUT | ER | 2026-01-30 | 2026-01-30 | 2026-01-30 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK5 | 0 | 2364 | 1370 | 0 | 3734 | 0 | - | 3734 | 2400 | 2230 | 2230 | 0 | 0 | Y | Y | Y |  | 3734 | 3261.2 | 0 | 3261.2 | 2230 | 2230 | 3261.2 | 1784 | 0 | 2026-01-29 | 2026-05-20 | - | 472.8 | 446 | HUAWEI |  |  |  | 0 | 110 | COMPLETED | IPRAN | 3261.2 | 2026-02-20 | 21 | 0 |  |  | 3261.2 | 472.8
EP26020026 | TME-REPIPRAN-TRT0135 | TRT0164_TRT0135_D_Retain_New_EAST_R3 | 2736.06 | 3734 | 2026-02-01 | TME | REPIPRAN | TRT0135 | BOONCHOT BORIWUT | ER | 2026-01-30 | 2026-01-30 | 2026-01-30 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK5 | 0 | 2364 | 1370 | 0 | 3734 | 0 | - | 3734 | 2400 | 2230 | 2230 | 0 | 0 | Y | Y | Y |  | 3734 | 3261.2 | 0 | 3261.2 | 2230 | 2230 | 3261.2 | 1784 | 0 | 2026-01-29 | 2026-05-20 | - | 472.8 | 446 | HUAWEI |  |  |  | 0 | 110 | COMPLETED | IPRAN | 3261.2 | 2026-02-20 | 21 | 0 |  |  | 3261.2 | 472.8
29742 | HAS-CC_Q425-PHOWY | PHOWY_2025 Capacity Expansion Ph7_EXP_SR | 9336.8 | 11671 | 2025-12-01 | HAS | CC_Q425 | PHOWY | NATTAWOOT SUWAN | SR | 2026-01-27 | 2026-01-28 | 2026-01-28 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Palagon Prommueangma | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK5 | 0 | 8563 | 2579 | 1586 | 12728 | 0 | - | 12728 | 9336.8 | 10182.4 | 10182.4 | 0 | 0 | Y | Y | Y |  | 13785 | 5719 | 0 | 5719 | 10182.4 | 10182.4 | 13785 | 10182.4 | 0 | 2026-01-28 | 2026-01-29 | - | 0 | 0 | HUAWEI | [7 empty] | 10899 | 2026-02-08 | 11 | 2886 | 2026-03-20 | 51 | 13785 | -1057
29692 | HAS-CC_Q425-SHNKM | SHNKM_2025 Capacity Expansion Ph4_EXP_SR | 11272 | 14090 | 2025-12-01 | HAS | CC_Q425 | SHNKM | NATTAWOOT SUWAN | SR | 2026-01-27 | 2026-01-28 | 2026-01-28 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK5 | 0 | 8934 | 2579 | 2577 | 14090 | 0 | - | 14090 | 11272 | 11272 | 11272 | 0 | 0 | Y | Y | Y |  | 14090 | 11409.8 | 0 | 11409.8 | 11272 | 11272 | 14090 | 9127.84 | 0 | 2026-01-27 | 2026-02-25 | - | 0 | 2144.16 | HUAWEI | [7 empty] | 11409.8 | 2026-02-08 | 11 | 2680.2 | 2026-03-15 | 46 | 14090 | 0
EP26020003 | HAE-Cap_Q126-NSCGM | NSCGM_2025 Capacity Expansion Ph8_EXP_ER | 19314.28 | 23554 | 2026-02-01 | HAE | Cap_Q126 | NSCGM | BOONCHOT BORIWUT | ER | 2026-02-06 | 2026-02-06 | 2026-02-06 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 16019 | 2579 | 4163 | 23554 | 7535 | 2026-02-23 | 31089 | 14603.48 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 31089 | 0 | 0 | 0 | 300 | 300 | 31089 | 300 | 4710.8 | 2026-02-09 | 2026-02-16 | - | 0 | 0 | HUAWEI |  |  |  | 3 | 10 | COMPLETED | MBB | 26283.3 | 2026-02-28 | 22 | 4805.7 | 2026-03-15 | 37 | 31089 | 0
EP26020005 | HAE-Cap_Q126-MKAOM | MKAOM_2025 Capacity Expansion Ph8_EXP_ER | 13363.54 | 16297 | 2026-02-01 | HAE | Cap_Q126 | MKAOM | BOONCHOT BORIWUT | ER | 2026-02-04 | 2026-02-04 | 2026-02-04 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 11339 | 2579 | 1586 | 16297 | 792 | 2026-02-23 | 17089 | 10104.14 | 8790 | 8490 | 300 | 0 | Y | Y | Y |  | 17089 | 0 | 0 | 0 | 8790 | 8790 | 17089 | 8790 | 0 | 2026-02-09 | 2026-02-13 | - | 0 | 0 | HUAWEI |  |  |  | 5 | 9 | COMPLETED | MBB | 13449.7 | 2026-02-28 | 24 | 3639.3 | 2026-03-15 | 39 | 17089 | 0
EP26020011 | HAE-Cap_Q126-TPRTM | TPRTM_2025 Capacity Expansion Ph8_EXP_ER | 10481.24 | 12782 | 2026-02-01 | HAE | Cap_Q126 | TPRTM | BOONCHOT BORIWUT | ER | 2026-02-04 | 2026-02-05 | 2026-02-05 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 7824 | 2579 | 1586 | 12782 | 1584 | 2026-02-23 | 14366 | 7924.84 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 21237 | 0 | 0 | 0 | 300 | 300 | 15952 | 300 | 2556.4 | 2026-02-15 | 2026-02-20 | - | 5285 | 0 | HUAWEI |  |  |  | 10 | 15 | COMPLETED | MBB | 16353.3 | 2026-02-28 | 23 | 4883.7 | 2026-03-15 | 38 | 21237 | -6871
EP26020012 | HAE-Cap_Q126-SUNGM | SUNGM_2025 Capacity Expansion Ph8_EXP_ER | 20659.08 | 25194 | 2026-02-01 | HAE | Cap_Q126 | SUNGM | BOONCHOT BORIWUT | ER | 2026-02-03 | 2026-02-03 | 2026-02-03 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 17659 | 2579 | 4163 | 25194 | 0 | - | 25194 | 15620.28 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 25194 | 0 | 0 | 0 | 300 | 300 | 25194 | 300 | 5038.8 | 2026-02-11 | 2026-02-16 | - | 0 | 0 | HUAWEI |  |  |  | 8 | 13 | COMPLETED | MBB | 19896.3 | 2026-02-28 | 25 | 5297.7 | 2026-03-15 | 40 | 25194 | 0
EP26020014 | HAE-Cap_Q126-DKBKM | DKBKM_2025 Capacity Expansion Ph8_EXP_ER | 13179.04 | 16072 | 2026-02-01 | HAE | Cap_Q126 | DKBKM | BOONCHOT BORIWUT | ER | 2026-02-06 | 2026-02-06 | 2026-02-06 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 8537 | 2579 | 4163 | 16072 | 528 | 2026-02-23 | 16600 | 9964.64 | 300 | 0 | 300 | 0 | Y | Y |  |  | 16600 | 12717.9 | 0 | 12717.9 | 360 | 240 | 16600 | 240 | 3214.4 | 2026-02-06 | 2026-02-10 | - | 0 | 60 | HUAWEI |  |  |  | 0 | 4 | COMPLETED | MBB | 13880.5 | 2026-02-14 | 8 | 2719.5 | 2026-03-15 | 37 | 16600 | 0
EP26020020 | HAE-Cap_Q126-BPGYM | BPGYM_2025 Capacity Expansion Ph8_EXP_ER | 13179.04 | 16072 | 2026-02-01 | HAE | Cap_Q126 | BPGYM | BOONCHOT BORIWUT | ER | 2026-02-05 | 2026-02-05 | 2026-02-05 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK6 | 793 | 8537 | 2579 | 4163 | 16072 | 1056 | 2026-02-23 | 17128 | 9964.64 | 7320 | 7020 | 300 | 0 | Y | Y |  |  | 17128 | 0 | 0 | 0 | 7380 | 7260 | 17128 | 7260 | 0 | 2026-02-10 | 2026-02-13 | - | 0 | 60 | HUAWEI |  |  |  | 5 | 8 | COMPLETED | MBB | 14250.1 | 2026-02-28 | 23 | 2877.9 | 2026-03-06 | 29 | 17128 | 0
EP26020049 | HAS-REP_MA-LMDIN | LMDIN_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-02-14 | HAS | REP_MA | LMDIN | NATTAWOOT SUWAN | SR | 2026-02-07 | 2026-02-07 | 2026-02-07 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK6 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y | Y |  | 9232 | 6462.4 | 0 | 6462.4 | 7385.6 | 7385.6 | 6462.4 | 5169.92 | 0 | 2026-02-08 | 2026-02-17 | - | 2769.6 | 2215.68 | HUAWEI | [7 empty] | 6462.4 | 2026-02-20 | 13 | 2769.6 | 2026-05-29 | 111 | 9232 | 0
EP26020043 | HAS-REP_MA-BGKHN | BGKHN_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-02-14 | HAS | REP_MA | BGKHN | NATTAWOOT SUWAN | SR | 2026-02-08 | 2026-02-08 | 2026-02-08 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK6 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y | Y |  | 9232 | 6462.4 | 0 | 6462.4 | 7385.6 | 7385.6 | 6462.4 | 5169.92 | 0 | 2026-02-10 | 2026-02-20 | - | 2769.6 | 2215.68 | HUAWEI | [7 empty] | 6462.4 | 2026-02-20 | 12 | 2769.6 | 2026-05-29 | 110 | 9232 | 0
EP26020044 | HAS-REP_MA-BKHAN | BKHAN_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-02-14 | HAS | REP_MA | BKHAN | NATTAWOOT SUWAN | SR | 2026-02-08 | 2026-02-08 | 2026-02-08 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK6 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y | Y |  | 9232 | 6462.4 | 0 | 6462.4 | 7385.6 | 7385.6 | 6462.4 | 5169.92 | 0 | 2026-02-09 | 2026-02-17 | - | 2769.6 | 2215.68 | HUAWEI | [7 empty] | 6462.4 | 2026-02-20 | 12 | 2769.6 | 2026-05-29 | 110 | 9232 | 0
EP26020001 | HAE-Cap_Q126-KHASM | KHASM_2025 Capacity Expansion Ph8_EXP_ER | 12810.86 | 15623 | 2026-02-13 | HAE | Cap_Q126 | KHASM | BOONCHOT BORIWUT | ER | 2026-02-10 | 2026-02-10 | 2026-02-10 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK7 | 793 | 8088 | 2579 | 4163 | 15623 | 1584 | 2026-02-23 | 17207 | 9686.26 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 17207 | 0 | 0 | 0 | 300 | 300 | 17207 | 240 | 3124.6 | 2026-02-19 | 2026-02-24 | - | 0 | 60 | HUAWEI |  |  |  | 9 | 14 | COMPLETED | MBB | 14305.4 | 2026-03-06 | 24 | 2901.6 | 2026-03-15 | 33 | 17207 | 0
EP26020004 | HAE-Cap_Q126-RSKBM | RSKBM_2025 Capacity Expansion Ph8_EXP_ER | 9765.38 | 11909 | 2026-02-13 | HAE | Cap_Q126 | RSKBM | BOONCHOT BORIWUT | ER | 2026-02-12 | 2026-02-13 | 2026-02-13 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK7 | 793 | 6951 | 2579 | 1586 | 11909 | 1452 | 2026-02-23 | 13361 | 7383.58 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 13361 | 0 | 0 | 0 | 300 | 300 | 13361 | 300 | 2381.8 | 2026-02-16 | 2026-02-19 | - | 0 | 0 | HUAWEI |  |  |  | 3 | 6 | COMPLETED | MBB | 10840.1 | 2026-02-28 | 15 | 2520.9 | 2026-03-06 | 21 | 13361 | 0
EP26020006 | HAE-Cap_Q126-PTHAM | PTHAM_2025 Capacity Expansion Ph8_EXP_ER | 9765.38 | 11909 | 2026-02-13 | HAE | Cap_Q126 | PTHAM | BOONCHOT BORIWUT | ER | 2026-02-12 | 2026-02-12 | 2026-02-12 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK7 | 793 | 6951 | 2579 | 1586 | 11909 | 1452 | 2026-02-23 | 13361 | 7383.58 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 14498 | 0 | 0 | 0 | 300 | 300 | 14498 | 300 | 2381.8 | 2026-02-13 | 2026-02-16 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 4 | COMPLETED | MBB | 11636 | 2026-02-28 | 16 | 2862 | 2026-03-06 | 22 | 14498 | -1137
EP26020010 | HAE-Cap_Q126-MBGAM | MBGAM_2025 Capacity Expansion Ph8_EXP_ER | 9765.38 | 11909 | 2026-02-13 | HAE | Cap_Q126 | MBGAM | BOONCHOT BORIWUT | ER | 2026-02-11 | 2026-02-11 | 2026-02-11 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK7 | 793 | 6951 | 2579 | 1586 | 11909 | 396 | 2026-02-23 | 12305 | 7383.58 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 12833 | 0 | 0 | 0 | 300 | 300 | 12833 | 300 | 2381.8 | 2026-02-16 | 2026-02-19 | - | 0 | 0 | HUAWEI |  |  |  | 5 | 8 | COMPLETED | MBB | 10470.5 | 2026-02-28 | 17 | 2362.5 | 2026-03-15 | 32 | 12833 | -528
EP26020015 | HAE-Cap_Q126-HAMHM | HAMHM_2025 Capacity Expansion Ph8_EXP_ER | 13179.04 | 16072 | 2026-02-13 | HAE | Cap_Q126 | HAMHM | BOONCHOT BORIWUT | ER | 2026-02-14 | 2026-02-14 | 2026-02-14 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK7 | 793 | 8537 | 2579 | 4163 | 16072 | 1452 | 2026-02-23 | 17524 | 9964.64 | 300 | 0 | 300 | 0 | Y | Y |  |  | 16996 | 0 | 0 | 0 | 540 | 60 | 16996 | 60 | 3214.4 | 2026-02-15 | 2026-02-17 | - | 0 | 240 | HUAWEI |  |  |  | 1 | 3 | COMPLETED | MBB | 14157.7 | 2026-02-28 | 14 | 2838.3 | 2026-03-06 | 20 | 16996 | 528
EP26020019 | HAE-Cap_Q126-CWKWM | CWKWM_2025 Capacity Expansion Ph8_EXP_ER | 14111.38 | 17209 | 2026-02-13 | HAE | Cap_Q126 | CWKWM | BOONCHOT BORIWUT | ER | 2026-02-10 | 2026-02-10 | 2026-02-10 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK7 | 793 | 9674 | 2579 | 4163 | 17209 | 1056 | 2026-02-23 | 18265 | 10669.58 | 7840 | 7540 | 300 | 0 | Y | Y |  |  | 18926 | 0 | 0 | 0 | 7900 | 7780 | 18926 | 7780 | 0 | 2026-02-11 | 2026-02-15 | - | 0 | 60 | HUAWEI |  |  |  | 1 | 5 | COMPLETED | MBB | 15508.7 | 2026-02-28 | 18 | 3417.3 | 2026-03-06 | 24 | 18926 | -661
EP26020029 | TME-DIS_ATN-CBR0549 | CBR0549-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CBR0549 | BOONCHOT BORIWUT | ER | 2026-02-11 | 2026-02-11 | 2026-02-11 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 2081 | 1230 | 0 | 2026-02-11 | 2026-02-23 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 12 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 17 | 394 | 2026-04-03 | 51 | 2081 | 0
EP26020030 | TME-DIS_ATN-CCO0015 | CCO0015-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CCO0015 | BOONCHOT BORIWUT | ER | 2026-02-10 | 2026-02-10 | 2026-02-10 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-10 | 2026-02-23 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 13 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 18 | 0 |  |  | 1687 | 394
EP26020031 | TME-DIS_ATN-CBI0073 | CBI0073-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CBI0073 | BOONCHOT BORIWUT | ER | 2026-02-12 | 2026-02-12 | 2026-02-12 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 2081 | 1230 | 0 | 2026-02-12 | 2026-02-23 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 11 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 16 | 394 | 2026-04-03 | 50 | 2081 | 0
EP26020032 | TME-DIS_ATN-CCO0016 | CCO0016-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CCO0016 | BOONCHOT BORIWUT | ER | 2026-02-10 | 2026-02-10 | 2026-02-10 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-10 | 2026-02-23 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 13 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 18 | 0 |  |  | 1687 | 394
EP26020033 | TME-DIS_ATN-CCO0135 | CCO0135-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CCO0135 | BOONCHOT BORIWUT | ER | 2026-02-11 | 2026-02-11 | 2026-02-11 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-11 | 2026-02-23 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 12 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 17 | 0 |  |  | 1687 | 394
EP26020035 | TME-DIS_ATN-CBR0034 | CBR0034-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CBR0034 | BOONCHOT BORIWUT | ER | 2026-02-11 | 2026-02-11 | 2026-02-11 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 2081 | 1230 | 0 | 2026-02-11 | 2026-02-23 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 12 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 17 | 394 | 2026-04-03 | 51 | 2081 | 0
EP26020036 | TME-DIS_ATN-CBI0137 | CBI0137-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CBI0137 | BOONCHOT BORIWUT | ER | 2026-02-12 | 2026-02-12 | 2026-02-12 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 2081 | 1230 | 0 | 2026-02-12 | 2026-02-23 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 11 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 16 | 394 | 2026-04-03 | 50 | 2081 | 0
EP26020057 | HAE-NEWSITE-CPWHM | CPWHM_2024 Coverage Expansion ph.2_New Site-Relocate_ER | 40268.56 | 49108 | 2026-02-13 | HAE | NEWSITE | CPWHM | BOONCHOT BORIWUT | ER | 2026-02-12 | 2026-02-16 | 2026-02-16 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 38992 | 7737 | 1586 | 49108 | 0 | - | 49108 | 30446.96 | 21695 | 21395 | 300 | 0 | Y | Y | Y |  | 49108 | 793 | 0 | 793 | 21695 | 21695 | 49108 | 21695 | 0 | 2026-02-18 | 2026-02-20 | - | 0 | 0 | HUAWEI |  |  |  | 2 | 4 | COMPLETED | MBB | 37410.4 | 2026-02-20 | 4 | 11697.6 | 2026-03-20 | 32 | 49108 | 0
29746 | HAS-CC_Q425-WNHST | WNHST_2025 Coverage Expansion Ph1_New_SR | 27632 | 34540 | 2025-12-01 | HAS | CC_Q425 | WNHST | NATTAWOOT SUWAN | SR | 2026-02-13 | 2026-02-13 | 2026-02-13 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK7 | 0 | 26805 | 5158 | 2577 | 34540 | 0 | - | 34540 | 27632 | 27208.8 | 27208.8 | 0 | 0 | Y | Y | Y |  | 34540 | 26498.5 | 317.1 | 26815.6 | 27208.8 | 27208.8 | 34540 | 20902.56 | 0 | 2026-02-04 | 2026-02-25 | - | 0 | 6306.24 | HUAWEI | [7 empty] | 26498.5 | 2026-02-14 | 1 | 8358.6 | 2026-02-14 | 1 | 34857.1 | -317.1
29691 | HAS-CC_Q425-PSKLN | PSKLN_2025 Capacity Expansion Ph6_EXP_SR | 9802.4 | 12253 | 2025-12-01 | HAS | CC_Q425 | PSKLN | NATTAWOOT SUWAN | SR | 2026-02-13 | 2026-02-13 | 2026-02-13 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Payon Sapphat | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK7 | 0 | 8088 | 2579 | 1586 | 12253 | 0 | - | 12253 | 9802.4 | 9802.4 | 9802.4 | 0 | 0 | Y | Y | Y |  | 13839 | 0 | 0 | 0 | 9802.4 | 9802.4 | 13839 | 9802.4 | 0 | 2026-02-05 | 2026-02-05 | - | 0 | 0 | HUAWEI | [7 empty] | 10936.8 | 2026-02-28 | 15 | 2902.2 | 2026-03-20 | 35 | 13839 | -1586
29069 | HAB-CovXPh2-A323A | A323A_2025 Capacity Expansion Ph3_EXP_BKK | 10161.6 | 12702 | 2025-09-01 | HAB | CovXPh2 | A323A | KHATHAHAT SITTHIHONG | BKK | 2026-01-29 | 2026-02-16 | 2026-02-16 | INHOUSE XAIPHONE KHONESOULIN | - | INHOUSE | Palagon Prommueangma | Apichart kampuang | 26WK8 | 793 | 7744 | 2579 | 1586 | 12702 | 0 | - | 12702 | 6986.1 | 300 | 0 | 300 | 0 | Y |  |  |  | 15675 | 0 | 0 | 0 | 0 | 0 | 14882 | 0 | 6195 | 2026-02-17 | 2026-02-18 | - | 793 | 300 | HUAWEI | [7 empty] | 12440 | 2026-03-06 | 18 | 2442 | 2026-04-18 | 61 | 14882 | -2180
EP26020054 | HAB-REPSFP-SMP2634 | SMP2634-AC-02_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-02-13 | HAB | REPSFP | SMP2634 | KHATHAHAT SITTHIHONG | BKK | 2026-02-03 | 2026-02-03 | 2026-02-03 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK6 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | 1453 | 1453 | 0 | 0 | Y | Y |  |  | 2081 | 0 | 0 | 0 | 0 | 0 | 2081 | 1453 | 0 | 2026-02-03 | 2026-02-13 | - | 0 | 0 | HUAWEI | [7 empty] | 1687 | 2026-02-28 | 25 | 394 | 2026-05-22 | 108 | 2081 | 0
EP26020055 | HAB-REPSFP-SMP2664 | SMP2664-AC-02_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-02-13 | HAB | REPSFP | SMP2664 | KHATHAHAT SITTHIHONG | BKK | 2026-02-03 | 2026-02-03 | 2026-02-03 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK6 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | 1453 | 1453 | 0 | 0 | Y | Y |  |  | 2081 | 0 | 0 | 0 | 0 | 0 | 2081 | 1178 | 0 | 2026-02-11 | 2026-02-13 | - | 0 | 275 | HUAWEI | [7 empty] | 1687 | 2026-02-28 | 25 | 394 | 2026-05-22 | 108 | 2081 | 0
EP26020056 | HAB-REPSFP-SMP0461 | SMP0461-AC-01_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-02-13 | HAB | REPSFP | SMP0461 | KHATHAHAT SITTHIHONG | BKK | 2026-02-03 | 2026-02-03 | 2026-02-03 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK6 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | 1453 | 1453 | 0 | 0 | Y | Y |  |  | 2081 | 0 | 0 | 0 | 0 | 0 | 2081 | 1453 | 0 | 2026-02-11 | 2026-02-13 | - | 0 | 0 | HUAWEI | [7 empty] | 1687 | 2026-02-28 | 25 | 394 | 2026-05-22 | 108 | 2081 | 0
EP26020047 | HAS-REP_MA-KNSWG | KNSWG_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-02-01 | HAS | REP_MA | KNSWG | NATTAWOOT SUWAN | SR | 2026-02-17 | 2026-02-17 | 2026-02-17 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK8 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7474.4 | 7385.6 | 7385.6 | 0 | 0 | Y | Y | Y |  | 9232 | 0 | 0 | 0 | 7385.6 | 7385.6 | 6462.4 | 5169.92 | 0 | 2026-02-17 | 2026-02-19 | - | 2769.6 | 2215.68 | HUAWEI | [7 empty] | 6462.4 | 2026-02-28 | 11 | 2769.6 | 2026-05-29 | 101 | 9232 | 0
EP26020045 | HAS-REP_MA-CLPLG | CLPLGC2_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-02-01 | HAS | REP_MA | CLPLG | NATTAWOOT SUWAN | SR | 2026-02-18 | 2026-02-18 | 2026-02-18 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK8 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7474.4 | 7385.6 | 7385.6 | 0 | 0 | Y | Y | Y |  | 9232 | 0 | 0 | 0 | 7385.6 | 7385.6 | 6462.4 | 5169.92 | 0 | 2026-02-18 | 2026-02-19 | - | 2769.6 | 2215.68 | HUAWEI | [7 empty] | 6462.4 | 2026-02-28 | 10 | 2769.6 | 2026-05-29 | 100 | 9232 | 0
EP26020007 | HAE-Cap_Q126-RMBTM | RMBTM_2025 Capacity Expansion Ph8_EXP_ER | 14935.48 | 18214 | 2026-02-13 | HAE | Cap_Q126 | RMBTM | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-19 | 2026-02-19 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 10679 | 2579 | 4163 | 18214 | 0 | - | 18214 | 11292.68 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 18214 | 0 | 0 | 0 | 300 | 300 | 18214 | 240 | 3642.8 | 2026-02-19 | 2026-03-02 | - | 0 | 60 | HUAWEI |  |  |  | 0 | 11 | COMPLETED | MBB | 15010.3 | 2026-02-28 | 9 | 3203.7 | 2026-03-06 | 15 | 18214 | 0
EP26020008 | HAE-Cap_Q126-MECPM | MECPM_2025 Capacity Expansion Ph8_EXP_ER | 9765.38 | 11909 | 2026-02-13 | HAE | Cap_Q126 | MECPM | BOONCHOT BORIWUT | ER | 2026-02-19 | 2026-02-19 | 2026-02-19 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 6951 | 2579 | 1586 | 11909 | 264 | 2026-02-23 | 12173 | 7383.58 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 12173 | 0 | 0 | 0 | 300 | 300 | 12173 | 240 | 2381.8 | 2026-02-25 | 2026-03-02 | - | 0 | 60 | HUAWEI |  |  |  | 6 | 11 | COMPLETED | MBB | 10008.5 | 2026-03-06 | 15 | 2164.5 | 2026-03-20 | 29 | 12173 | 0
EP26020009 | HAE-Cap_Q126-SBWMM | SBWMM_2025 Capacity Expansion Ph8_EXP_ER | 15802.22 | 19271 | 2026-02-13 | HAE | Cap_Q126 | SBWMM | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 11736 | 2579 | 4163 | 19271 | 0 | - | 19271 | 11948.02 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 19271 | 0 | 0 | 0 | 300 | 300 | 19271 | 240 | 3854.2 | 2026-02-20 | 2026-02-25 | - | 0 | 60 | HUAWEI |  |  |  | 3 | 8 | COMPLETED | MBB | 15750.2 | 2026-03-06 | 17 | 3520.8 | 2026-03-06 | 17 | 19271 | 0
EP26020013 | HAE-Cap_Q126-TPSEM | TPSEM_2025 Capacity Expansion Ph8_EXP_ER | 15369.26 | 18743 | 2026-02-13 | HAE | Cap_Q126 | TPSEM | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 11208 | 2579 | 4163 | 18743 | 0 | - | 18743 | 11620.66 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 18743 | 0 | 0 | 0 | 300 | 300 | 18743 | 240 | 3748.6 | 2026-02-18 | 2026-03-02 | - | 0 | 60 | HUAWEI |  |  |  | 1 | 13 | COMPLETED | MBB | 15380.6 | 2026-02-28 | 11 | 3362.4 | 2026-03-20 | 31 | 18743 | 0
EP26020016 | HAE-Cap_Q126-BOBKM | BOBKM_2025 Capacity Expansion Ph8_EXP_ER | 13352.88 | 16284 | 2026-02-13 | HAE | Cap_Q126 | BOBKM | BOONCHOT BORIWUT | ER | 2026-02-11 | 2026-02-18 | 2026-02-18 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 8749 | 2579 | 4163 | 16284 | 1056 | 2026-02-23 | 17340 | 10096.08 | 7390 | 7090 | 300 | 0 | Y | Y | Y |  | 17340 | 0 | 0 | 0 | 7390 | 7390 | 17340 | 7330 | 0 | 2026-02-19 | 2026-02-21 | - | 0 | 60 | HUAWEI |  |  |  | 1 | 3 | COMPLETED | MBB | 14398.5 | 2026-03-06 | 16 | 2941.5 | 2026-03-06 | 16 | 17340 | 0
EP26020018 | HAE-Cap_Q126-BTJMM | BTJMM_2025 Capacity Expansion Ph8_EXP_ER | 24149.82 | 29451 | 2026-02-13 | HAE | Cap_Q126 | BTJMM | BOONCHOT BORIWUT | ER | 2026-02-19 | 2026-02-19 | 2026-02-19 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK8 | 793 | 21916 | 2579 | 4163 | 29451 | 0 | - | 29451 | 18259.62 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 29451 | 0 | 0 | 0 | 300 | 300 | 29451 | 240 | 5890.2 | 2026-02-26 | 2026-03-02 | - | 0 | 60 | HUAWEI |  |  |  | 7 | 11 | COMPLETED | MBB | 22876.2 | 2026-03-06 | 15 | 6574.8 | 2026-03-20 | 29 | 29451 | 0
EP26020027 | TME-DIS_ATN-CBR0715 | CBR0715-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CBR0715 | BOONCHOT BORIWUT | ER | 2026-02-16 | 2026-02-16 | 2026-02-16 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 2081 | 1230 | 0 | 2026-02-16 | 2026-02-23 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 12 | 394 | 2026-04-03 | 46 | 2081 | 0
EP26020028 | TME-DIS_ATN-CBI0357 | CBI0357-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CBI0357 | BOONCHOT BORIWUT | ER | 2026-02-16 | 2026-02-16 | 2026-02-16 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 2081 | 1230 | 0 | 2026-02-16 | 2026-02-23 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 12 | 394 | 2026-04-03 | 46 | 2081 | 0
EP26020082 | TME-REPIPRAN-TRT0001 | TRT0001_D_AGG_Exp_EAST_R3 | 3417.82 | 4413 | 2026-02-13 | TME | REPIPRAN | TRT0001 | BOONCHOT BORIWUT | ER | 2026-02-16 | 2026-02-16 | 2026-02-16 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 4413 | 0 | 0 | 4413 | 0 | - | 4413 | 2800 | 2800 | 2800 | 0 | 0 | Y | Y | Y |  | 4413 | 0 | 0 | 0 |  | 2800 | 3530.4 | 2800 | 0 | 2026-02-17 | 2026-02-20 | - | 882.6 | 0 | HUAWEI |  |  |  | 1 | 4 | COMPLETED | IPRAN | 3530.4 | 2026-02-28 | 12 | 0 |  |  | 3530.4 | 882.6
EP26020073 | TME-DIS_ATN-RYG0021 | RYG0021-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | RYG0021 | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-17 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 8 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 11 | 0 |  |  | 1687 | 394
EP26020074 | TME-DIS_ATN-RYG0303 | RYG0303-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | RYG0303 | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-17 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 8 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 11 | 0 |  |  | 1687 | 394
EP26020063 | TME-DIS_ATN-RYG0307 | RYG0307-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | RYG0307 | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-17 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 8 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 11 | 0 |  |  | 1687 | 394
EP26020067 | TME-DIS_ATN-SKE0009 | SKE0009-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | SKE0009 | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-17 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 8 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 11 | 0 |  |  | 1687 | 394
EP26020072 | TME-DIS_ATN-SKO0094 | SKO0094-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | SKO0094 | BOONCHOT BORIWUT | ER | 2026-02-17 | 2026-02-17 | 2026-02-17 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-03-11 | - | 394 | 0 | HUAWEI |  |  |  | 1 | 22 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 17 | 0 |  |  | 1687 | 394
EP26020069 | TME-DIS_ATN-CTB0014 | CTB0014-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CTB0014 | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-18 | 2026-02-18 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 10 | 0 |  |  | 1687 | 394
EP26020070 | TME-DIS_ATN-CTI0012 | CTI0012-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CTI0012 | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-18 | 2026-02-18 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 10 | 0 |  |  | 1687 | 394
EP26020062 | TME-DIS_ATN-CTI0023 | CTI0023-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CTI0023 | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-18 | 2026-02-18 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-02-28 | 10 | 0 |  |  | 1687 | 394
EP26020071 | TME-DIS_ATN-NYK0008 | NYK0008-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | NYK0008 | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-18 | 2026-02-18 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 16 | 0 |  |  | 1687 | 394
EP26020058 | TME-DIS_ATN-NYK0019 | NYK0019-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | NYK0019 | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-18 | 2026-02-18 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-18 | 2026-02-25 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 16 | 0 |  |  | 1687 | 394
EP26020059 | TME-DIS_ATN-PRI0004 | PRI0004-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | PRI0004 | BOONCHOT BORIWUT | ER | 2026-02-19 | 2026-02-19 | 2026-02-19 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-19 | 2026-03-05 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 14 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 15 | 0 |  |  | 1687 | 394
EP26020061 | TME-DIS_ATN-PRI0006 | PRI0006-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | PRI0006 | BOONCHOT BORIWUT | ER | 2026-02-19 | 2026-02-19 | 2026-02-19 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-19 | 2026-03-05 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 14 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 15 | 0 |  |  | 1687 | 394
EP26020064 | TME-DIS_ATN-TRT0120 | TRT0120-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | TRT0120 | BOONCHOT BORIWUT | ER | 2026-02-19 | 2026-02-19 | 2026-02-19 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-19 | 2026-03-05 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 14 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 15 | 0 |  |  | 1687 | 394
EP26020066 | TME-DIS_ATN-TRT0006 | TRT0006-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | TRT0006 | BOONCHOT BORIWUT | ER | 2026-02-20 | 2026-02-20 | 2026-02-20 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-20 | 2026-03-11 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 19 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 14 | 0 |  |  | 1687 | 394
EP26020068 | TME-DIS_ATN-TRT0165 | TRT0165-AC-02_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | TRT0165 | BOONCHOT BORIWUT | ER | 2026-02-20 | 2026-02-20 | 2026-02-20 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1230 | 1230 | 0 | 0 | Y | Y | Y |  | 2081 | 0 | 0 | 0 | 1230 | 1230 | 1687 | 1230 | 0 | 2026-02-20 | 2026-03-05 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 13 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 14 | 0 |  |  | 1687 | 394
EP26020052 | HAS-CC_Q126-SRKJN | SRKJN_2025 Coverage Expansion Ph1_New_SR | 33224.8 | 39088 | 2026-02-01 | HAS | CC_Q126 | SRKJN | NATTAWOOT SUWAN | SR | 2026-02-24 | 2026-02-24 | 2026-02-24 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 31353 | 5158 | 2577 | 39088 | 0 | - | 39088 | 31270.4 | 30847.2 | 30847.2 | 0 | 0 | Y | Y | Y |  | 39088 |  |  |  | 30847.2 | 30847.2 | 39088 | 23449.44 | 0 | 2026-02-25 | 2026-03-04 | - | 0 | 7397.76 | HUAWEI | [7 empty] | 29682.1 | 2026-03-15 | 19 | 9405.9 | 2026-03-20 | 24 | 39088 | 0
29835 | HAS-REP_MA-CDPLS | CDPLS_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | CDPLS | NATTAWOOT SUWAN | SR | 2026-02-26 | 2026-02-26 | 2026-02-26 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 11628 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-27 | 2026-03-21 | - | 7558.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-15 | 17 | 1744.2 | 2026-05-29 | 92 | 5814 | 0
29837 | HAS-REP_MA-WTSAI | WTSAI_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | WTSAI | NATTAWOOT SUWAN | SR | 2026-02-26 | 2026-02-26 | 2026-02-26 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 11628 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-28 | 2026-03-21 | - | 7558.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-15 | 17 | 1744.2 | 2026-05-29 | 92 | 5814 | 0
29841 | HAS-REP_MA-YAPAN | YAPAN_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | YAPAN | NATTAWOOT SUWAN | SR | 2026-02-26 | 2026-02-26 | 2026-02-26 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 11628 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-27 | 2026-03-21 | - | 7558.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-15 | 17 | 1744.2 | 2026-05-29 | 92 | 5814 | 0
29829 | HAS-REP_MA-NSNCH | NSNCH_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | NSNCH | NATTAWOOT SUWAN | SR | 2026-02-27 | 2026-02-27 | 2026-02-27 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 5814 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-25 | 2026-03-21 | - | 1744.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-20 | 21 | 1744.2 | 2026-05-29 | 91 | 5814 | 0
29830 | HAS-REP_MA-OPCPN | OPCPN_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | OPCPN | NATTAWOOT SUWAN | SR | 2026-02-28 | 2026-02-28 | 2026-02-28 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 11628 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-28 | 2026-03-21 | - | 7558.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-15 | 15 | 1744.2 | 2026-05-29 | 90 | 5814 | 0
29831 | HAS-REP_MA-SWGTI | SWGTI_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | SWGTI | NATTAWOOT SUWAN | SR | 2026-02-28 | 2026-02-28 | 2026-02-28 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 11628 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-27 | 2026-03-21 | - | 7558.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-15 | 15 | 1744.2 | 2026-05-29 | 90 | 5814 | 0
29827 | HAS-REP_MA-STHNC | STHNC_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | STHNC | NATTAWOOT SUWAN | SR | 2026-02-28 | 2026-02-28 | 2026-02-28 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK9 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 4651.2 | 4651.2 | 4651.2 | 0 | 0 | Y | Y | Y |  | 5814 |  |  |  | 4651.2 | 4651.2 | 4069.8 | 3255.84 | 0 | 2026-02-28 | 2026-03-21 | - | 1744.2 | 1395.36 | HUAWEI | [7 empty] | 4069.8 | 2026-03-15 | 15 | 1744.2 | 2026-05-29 | 90 | 5814 | 0
29509 | TRE-D850Q425-RYG0105D | D_RYG0105 |  |  | 2025-10-01 | TRE | D850Q425 | RYG0105D | BOONCHOT BORIWUT | ER | 2026-02-24 | 2026-02-24 | 2026-02-24 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | BOONCHOT BORIWUT | BOONCHOT BORIWUT | 26WK9 |  |  |  |  | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | Y | [9 empty] | 0 | 0 |  |  |  | - | 0 | 0 | TRUE | [5 empty] | COMPLETED | DISMANTLE | 0 |  |  | 0 |  |  | 0 | 0
29578 | TRS-D850Q425-PTN0015D | D_PTN0015 |  |  | 2025-10-01 | TRS | D850Q425 | PTN0015D | NATTAWOOT SUWAN | SR | 2026-02-27 | 2026-02-27 | 2026-02-27 | บริษัท บี โอ เอส ซี จำกัด | VD01223 | ALLY | Payon Sapphat | บริษัท บี โอ เอส ซี จำกัด | 26WK9 |  |  |  |  | 0 | 0 | - | 0 | 19084.1163 | [14 empty] | 0 | 0 | 0 |  |  | - | 0 | 0 | TRUE | [7 empty] | 0 |  |  | 0 |  |  | 0 | 0
EP26020075 | HAE-Cap_Q126-NWKYM | NWKYM_2025 Capacity Expansion Ph8_EXP_ER | 10415.64 | 12702 | 2026-02-13 | HAE | Cap_Q126 | NWKYM | BOONCHOT BORIWUT | ER | 2026-02-23 | 2026-02-23 | 2026-02-23 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK9 | 793 | 10323 | 0 | 1586 | 12702 | 0 | - | 12702 | 7875.24 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 13759 |  |  |  | 300 | 300 | 13759 | 300 | 2540.4 | 2026-02-23 | 2026-03-02 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 7 | COMPLETED | MBB | 11118.7 | 2026-03-06 | 11 | 2640.3 | 2026-03-20 | 25 | 13759 | -1057
EP26020076 | HAE-Cap_Q126-NREKM | NREKM_2025 Capacity Expansion Ph8_EXP_ER | 9765.38 | 11909 | 2026-02-13 | HAE | Cap_Q126 | NREKM | BOONCHOT BORIWUT | ER | 2026-02-23 | 2026-02-23 | 2026-02-23 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK9 | 793 | 9530 | 0 | 1586 | 11909 | 1056 | - | 12965 | 7383.58 | 6570 | 6270 | 300 | 0 | Y | Y | Y |  | 12965 |  |  |  | 6570 | 6570 | 12965 | 6570 | 0 | 2026-02-24 | 2026-02-26 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 3 | COMPLETED | MBB | 10562.9 | 2026-03-06 | 11 | 2402.1 | 2026-03-15 | 20 | 12965 | 0
EP26020078 | HAE-Cap_Q126-WNUKM | WNUKM_2025 Capacity Expansion Ph8_EXP_ER | 9765.38 | 11909 | 2026-02-13 | HAE | Cap_Q126 | WNUKM | BOONCHOT BORIWUT | ER | 2026-02-23 | 2026-02-24 | 2026-02-24 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK9 | 793 | 9530 | 0 | 1586 | 11909 | 0 | - | 11909 | 7383.58 | 300 | 0 | 300 | 0 | Y | Y | Y |  | 12965 |  |  |  | 300 | 300 | 12965 | 300 | 2381.8 | 2026-02-25 | 2026-02-26 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 2 | COMPLETED | MBB | 10562.9 | 2026-03-06 | 10 | 2402.1 | 2026-03-15 | 19 | 12965 | -1056
EP26020083 | TME-DIS_ATN-CCO0017 | CCO0017-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CCO0017 | BOONCHOT BORIWUT | ER | 2026-02-24 | 2026-02-24 | 2026-02-24 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1301.1 | 1301.1 | 0 | 0 | Y | Y | Y |  | 2081 |  |  |  | 1301.1 | 1301.1 | 1687 | 1301.1 | 0 | 2026-02-24 | 2026-03-05 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 9 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 10 | 0 |  |  | 1687 | 394
EP26020084 | TME-DIS_ATN-CCO0011 | CCO0011-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CCO0011 | BOONCHOT BORIWUT | ER | 2026-02-24 | 2026-02-24 | 2026-02-24 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1301.1 | 1301.1 | 0 | 0 | Y | Y | Y |  | 2081 |  |  |  |  | 1301.1 | 1687 | 1301.1 | 0 | 2026-02-24 | 2026-03-09 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 13 | COMPLETED | IPRAN | 1687 | 2026-03-15 | 19 | 0 |  |  | 1687 | 394
EP26020085 | TME-DIS_ATN-CCS0263 | CCS0263-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-02-13 | TME | DIS_ATN | CCS0263 | BOONCHOT BORIWUT | ER | 2026-02-24 | 2026-02-24 | 2026-02-24 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | 1301.1 | 1301.1 | 0 | 0 | Y | Y | Y |  | 2081 |  |  |  |  | 1301.1 | 1687 | 1301.1 | 0 | 2026-02-24 | 2026-03-05 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 9 | COMPLETED | IPRAN | 1687 | 2026-03-06 | 10 | 0 |  |  | 1687 | 394
EP26020086 | TME-REPSFP-PCR0068 | PCR0068-AC-01-PCR0125-AC-01_D_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-02-13 | TME | REPSFP | PCR0068 | BOONCHOT BORIWUT | ER | 2026-02-19 | 2026-02-19 | 2026-02-19 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-19 | 2026-02-24 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 5 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 15 | 0 |  |  | 3043.2 | 760.8
EP26020087 | TME-NCE_Q126-CBR0529 | CBR0529_D_NCE_Swap_EAST_R3 | 3907.59 | 5054.2 | 2026-02-13 | TME | NCE_Q126 | CBR0529 | BOONCHOT BORIWUT | ER | 2026-02-24 | 2026-02-24 | 2026-02-24 | บริษัท สุพรรณ เทเลคอม จำกัด | VD00327 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK9 | 0 | 4711.2 | 0 | 343 | 5054.2 | 0 | - | 5054.2 | 3200 | 3199.82 | 3199.82 | 0 | 0 | Y | Y |  |  | 5054.2 |  |  |  | 3200.2 | 3200.2 | 4111.96 | 3200.2 | 0 | 2026-02-25 | 2026-02-26 | - | 942.24 | -0.38 | HUAWEI |  |  |  | 1 | 2 | COMPLETED | IPRAN | 4111.96 | 2026-03-06 | 10 | 0 |  |  | 4111.96 | 942.24
EP26030001 | TME-REPSFP-CBI0149 | CBI0149-AC-02-CBR0149-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-14 | TME | REPSFP | CBI0149 | BOONCHOT BORIWUT | ER | 2026-02-26 | 2026-02-26 | 2026-02-26 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-26 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 5 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 8 | 0 |  |  | 3043.2 | 760.8
EP26030002 | TME-REPSFP-CBI0184D | CBI0184-AC-01-CBR1428-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-15 | TME | REPSFP | CBI0184D | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-25 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030003 | TME-REPSFP-CBI0639 | CBI0639-AC-01-CBR0336-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-16 | TME | REPSFP | CBI0639 | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-25 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030004 | TME-REPSFP-CBR0148 | CBR0148-AC-01-CBI0016-AG-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-17 | TME | REPSFP | CBR0148 | BOONCHOT BORIWUT | ER | 2026-03-02 | 2026-03-02 | 2026-03-02 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK10 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-02-26 | 2026-03-04 | - | 760.8 | 480 | HUAWEI |  |  |  | 0 | 2 | COMPLETED | IPRAN | 3043.2 | 2026-03-20 | 18 | 0 |  |  | 3043.2 | 760.8
EP26030005 | TME-REPSFP-CBR0192 | CBR0192-AC-01-CBR0148-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-18 | TME | REPSFP | CBR0192 | BOONCHOT BORIWUT | ER | 2026-02-26 | 2026-02-26 | 2026-02-26 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-26 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 5 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 8 | 0 |  |  | 3043.2 | 760.8
EP26030006 | TME-REPSFP-CBR0379 | CBR0379-AC-01-CBR1047-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-19 | TME | REPSFP | CBR0379 | BOONCHOT BORIWUT | ER | 2026-02-26 | 2026-02-26 | 2026-02-26 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-26 | 2026-03-04 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 8 | 0 |  |  | 3043.2 | 760.8
EP26030007 | TME-REPSFP-CBR0819 | CBR0819-AC-01-CBR0789-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-20 | TME | REPSFP | CBR0819 | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-25 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030008 | TME-REPSFP-CBR0898 | CBR0898-AC-01-CBR1017-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-21 | TME | REPSFP | CBR0898 | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-25 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030010 | TME-REPSFP-CBR1406 | CBR1406-AC-01-CBRC056-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-23 | TME | REPSFP | CBR1406 | BOONCHOT BORIWUT | ER | 2026-02-26 | 2026-02-26 | 2026-02-26 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-26 | 2026-03-04 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 8 | 0 |  |  | 3043.2 | 760.8
EP26030011 | TME-REPSFP-CBR1428 | CBR1428-AC-01-CBR1274-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-24 | TME | REPSFP | CBR1428 | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-25 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030012 | TME-REPSFP-CBR1429 | CBR1429-AC-01-CBR1428-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-25 | TME | REPSFP | CBR1429 | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-25 | 2026-03-12 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 15 | COMPLETED | IPRAN | 3043.2 | 2026-03-20 | 23 | 0 |  |  | 3043.2 | 760.8
EP26030013 | TME-REPSFP-CBR1430 | CBR1430-AC-01-CBR0148-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-26 | TME | REPSFP | CBR1430 | BOONCHOT BORIWUT | ER | 2026-02-26 | 2026-02-26 | 2026-02-26 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-26 | 2026-03-04 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 8 | 0 |  |  | 3043.2 | 760.8
EP26030014 | TME-REPSFP-CBI0058 | CBI0058-AC-02-CBR0058-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-29 | TME | REPSFP | CBI0058 | BOONCHOT BORIWUT | ER | 2026-02-25 | 2026-02-25 | 2026-02-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK9 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y | Y |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-02-26 | 2026-03-03 | - | 760.8 | 0 | HUAWEI |  |  |  | 1 | 6 | COMPLETED | IPRAN | 3043.2 | 2026-03-06 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030048 | HAB-REPSFP-BKK2508A | BKK2508-AC-02_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-03-01 | HAB | REPSFP | PCR4004 | KHATHAHAT SITTHIHONG | BKK | 2026-03-04 | 2026-03-04 | 2026-03-04 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK10 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | 1453 | 1453 | 0 | 0 | Y | Y |  |  | 2081 | [5 empty] | 1687 | 1453 | 0 | 2026-03-04 | 2026-03-16 | - | 394 | 0 | HUAWEI | [7 empty] | 1687 | 2026-04-03 | 30 | 0 |  |  | 1687 | 394
EP26030052 | HAB-REPSFP-PCR4004 | DN_PCR4004_PCR0006-AC-02_D_Rehoming_Bidi_EAST_R3 | 2800.5 | 3734 | 2026-03-01 | HAB | REPSFP | PCR4004 | KHATHAHAT SITTHIHONG | BKK | 2026-02-25 | 2026-02-25 | 2026-02-25 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK9 | 0 | 2364 | 1370 | 0 | 3734 | 0 | - | 3734 | 2613.8 | 2590 | 2590 | 0 | 0 | Y | Y |  |  | 3734 | [5 empty] | 3261.2 | 2590 | 0 | 2026-02-25 |  | - | 472.8 | 0 | HUAWEI | [7 empty] | 3261.2 | 2026-04-03 | 37 | 0 |  |  | 3261.2 | 472.8
EP26030053 | HAB-REPSFP-PCR0157 | DN_PCR4004_PCR0157-AC-01_D_Rehoming_Bidi_EAST_R3 | 5601 | 7468 | 2026-03-01 | HAB | REPSFP | PCR0157 | KHATHAHAT SITTHIHONG | BKK | 2026-02-26 | 2026-02-26 | 2026-02-26 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK9 | 0 | 4728 | 2740 | 0 | 7468 | 0 | - | 7468 | 5227.6 | 4230 | 4230 | 0 | 0 | Y | Y |  |  | 7468 | [5 empty] | 6522.4 | 4230 | 0 | 2026-02-26 |  | - | 945.6 | 0 | HUAWEI | [7 empty] | 6522.4 | 2026-04-03 | 36 | 0 |  |  | 6522.4 | 945.6
EP26030054 | HAB-REPSFP-PCR2067 | PN_PCR2067_PCR0051-AC-01_D_Rehoming_Bidi_EAST_R3 | 5601 | 7468 | 2026-03-01 | HAB | REPSFP | PCR2067 | KHATHAHAT SITTHIHONG | BKK | 2026-02-25 | 2026-02-25 | 2026-02-25 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK9 | 0 | 4728 | 2740 | 0 | 7468 | 0 | - | 7468 | 5227.6 | 4230 | 4230 | 0 | 0 | Y | Y |  |  | 7468 | [5 empty] | 6522.4 | 4230 | 0 | 2026-02-25 |  | - | 945.6 | 0 | HUAWEI | [7 empty] | 6522.4 | 2026-04-03 | 37 | 0 |  |  | 6522.4 | 945.6
EP26030055 | HAB-REPSFP-PRI0001A | PN_PCR2067_PRI0001-AG-01_D_Rehoming_Bidi_EAST_R3 | 2800.5 | 3734 | 2026-03-01 | HAB | REPSFP | PRI0001A | KHATHAHAT SITTHIHONG | BKK | 2026-02-25 | 2026-02-25 | 2026-02-25 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK9 | 0 | 2364 | 1370 | 0 | 3734 | 0 | - | 3734 | 2613.8 | 2590 | 2590 | 0 | 0 | Y | Y |  |  | 3734 | [5 empty] | 3261.2 | 2590 | 0 | 2026-02-25 |  | - | 472.8 | 0 | HUAWEI | [7 empty] | 3261.2 | 2026-04-03 | 37 | 0 |  |  | 3261.2 | 472.8
EP26030157 | HAB-REPSFP-SMP0694B | SMP0694-AC-01_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-03-01 | HAB | REPSFP | SMP0694B | KHATHAHAT SITTHIHONG | BKK | 2026-02-12 | 2026-02-12 | 2026-02-12 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK7 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | [8 empty] | 2081 | [5 empty] | 2081 | 0 | 0 | 2026-02-12 | 2026-02-13 | - | 0 | 0 | HUAWEI | [7 empty] | 3374 | 2026-04-18 | 65 | 394 | 2026-05-22 | 99 | 3768 | -1687
EP26030158 | HAB-REPSFP-SMP2576B | SMP2576-AC-02_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-03-01 | HAB | REPSFP | SMP2576B | KHATHAHAT SITTHIHONG | BKK | 2026-02-04 | 2026-02-04 | 2026-02-04 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK6 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | [8 empty] | 2081 | [5 empty] | 2081 | 0 | 0 | 2026-02-04 | 2026-02-13 | - | 0 | 0 | HUAWEI | [7 empty] | 3374 | 2026-04-18 | 73 | 394 | 2026-05-22 | 107 | 3768 | -1687
EP26020053 | HAS-CC_Q126-MSKHH | MSKHH_2025 Coverage Expansion Ph1_New_SR | 20312.45 | 23897 | 2026-02-13 | HAS | CC_Q126 | MSKHH | NATTAWOOT SUWAN | SR | 2026-03-04 | 2026-03-07 | 2026-03-07 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK10 | 0 | 18741 | 2579 | 2577 | 23897 | 0 | - | 23897 | 19117.6 | 19117.6 | 19117.6 | 0 | 0 | Y | Y | Y |  | 23897 |  |  |  | 19117.6 | 19117.6 | 23897 | 14619.76 | 0 | 2026-03-06 | 2026-03-09 | - | 0 | 4497.84 | HUAWEI | [7 empty] | 18274.7 | 2026-03-20 | 13 | 5622.3 | 2026-04-03 | 27 | 23897 | 0
EP26020079 | HAE-Cap_Q126-KKFJM | KKFJM_2025 Capacity Expansion Ph5_EXP_ER_Add | 12583.72 | 15346 | 2026-02-13 | HAE | Cap_Q126 | KKFJM | BOONCHOT BORIWUT | ER | - | - |  | INHOUSE PHET SAITHONG | - | CANCEL | CANCEL | CANCEL |  | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 9514.52 | 0 | 0 | 0 | 0 | - | - | - | 793 | - | [5 empty] | 0 | 0 | 0 | - | - | - | 0 | 0 | - | [5 empty] | CANCEL | CANCEL | 793 |  |  | 0 |  |  | 793 | -793
EP26030015 | TME-AGG_Exp-RYG0004 | RYG0004_D_AGG_Exp_EAST_R3 | 3417.82 | 4413 | 2026-03-30 | TME | AGG_Exp | RYG0004 | BOONCHOT BORIWUT | ER | 2026-03-06 | 2026-03-06 | 2026-03-06 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK10 | 0 | 4413 | 0 | 0 | 4413 | 0 | - | 4413 | 2800 | 2800 | 2800 | 0 | 0 | Y | Y | Y |  | 4413 |  |  |  | 2800 | 2800 | 3530.4 | 2240 | 0 | 2026-03-06 | 2026-03-09 | - | 882.6 | 560 | HUAWEI |  |  |  | 0 | 3 | COMPLETED | IPRAN | 3530.4 | 2026-04-03 | 28 | 0 |  |  | 3530.4 | 882.6
EP26030049 | HAB-REPSFP-BKK0650A | BKK0650-AC-01_D_Dismantle_EAST_R3 | 1560.75 | 2081 | 2026-03-01 | HAB | REPSFP | BKK0650A | KHATHAHAT SITTHIHONG | BKK | 2026-03-06 | 2026-03-06 | 2026-03-06 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK10 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | 1453 | 1453 | 0 | 0 | Y | Y |  |  | 2081 | [5 empty] | 1687 | 1453 | 0 | 2026-03-06 | 2026-03-16 | - | 394 | 0 | HUAWEI | [7 empty] | 1687 | 2026-04-03 | 28 | 0 |  |  | 1687 | 394
EP26030050 | HAB-REPSFP-SMP0668 | SMP0668-AC-01_D_Dismantle_BMA_R2 | 1560.75 | 2081 | 2026-03-01 | HAB | REPSFP | SMP0668 | KHATHAHAT SITTHIHONG | BKK | 2026-03-05 | 2026-03-05 | 2026-03-05 | บริษัท ทีเอฟแอล ทีมีส จำกัด | VD01007 | ALLY | KHATHAHAT SITTHIHONG | บริษัท ทีเอฟแอล ทีมีส จำกัด | 26WK10 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1456.7 | 1453 | 1453 | 0 | 0 | Y | Y |  |  | 2081 | [5 empty] | 1687 | 1453 | 0 | 2026-03-05 | 2026-03-17 | - | 394 | 0 | HUAWEI | [7 empty] | 1687 | 2026-04-03 | 29 | 0 |  |  | 1687 | 394
EP26030040 | HAS-REP_MA-HTRCH | HTRCH_2025_Imp_UPS_SR | 4941.9 | 5814 | 2026-03-01 | HAS | REP_MA | HTRCH | NATTAWOOT SUWAN | SR | 2026-03-09 | 2026-03-09 | 2026-03-09 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK11 | 0 | 5814 | 0 | 0 | 5814 | 0 | - | 5814 | 9302.4 | 4651.2 | 4651.2 | 0 | 0 | Y | Y |  |  | 11628 | [5 empty] | 4069.8 | 0 | 0 | 2026-03-09 |  | - | 7558.2 | 4651.2 | HUAWEI | [7 empty] | 4069.8 | 2026-03-20 | 11 | 1744.2 | 2026-05-29 | 81 | 5814 | 0
EP26030016 | HAS-CC_Q126-LWASE | LWASE_2025 Coverage Expansion Ph1_New_SR | 20312.45 | 23897 | 2026-03-01 | HAS | CC_Q126 | LWASE | NATTAWOOT SUWAN | SR | 2026-03-10 | 2026-03-10 | 2026-03-10 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK11 | 0 | 18741 | 2579 | 2577 | 23897 | 0 | - | 23897 | 19117.6 | 19117.6 | 19117.6 | 0 | 0 | Y | Y |  |  | 23897 | [5 empty] | 23897 | 0 | 0 | 2026-03-10 | 2026-03-17 | - | 0 | 19117.6 | HUAWEI | [7 empty] | 18274.7 | 2026-03-20 | 10 | 5622.3 | 2026-04-03 | 24 | 23897 | 0
EP26030017 | HAS-REP_MA-NGYUN | NGYUN_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | NGYUN | NATTAWOOT SUWAN | SR | 2026-03-14 | 2026-03-14 | 2026-03-14 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK11 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-14 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-03-20 | 6 | 2769.6 | 2026-05-29 | 76 | 9232 | 0
EP26030024 | HAS-REP_MA-RILUG | RILUG_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | RILUG | NATTAWOOT SUWAN | SR | 2026-03-14 | 2026-03-14 | 2026-03-14 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK11 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-14 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-03-20 | 6 | 2769.6 | 2026-05-29 | 76 | 9232 | 0
EP26030023 | HAS-REP_MA-PSUTM | PSUTM_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | PSUTM | NATTAWOOT SUWAN | SR | 2026-03-15 | 2026-03-15 | 2026-03-15 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK11 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-15 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-03-20 | 5 | 2769.6 | 2026-05-29 | 75 | 9232 | 0
EP26030026 | HAS-REP_MA-SYNLA | SYNLA_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | SYNLA | NATTAWOOT SUWAN | SR | 2026-03-15 | 2026-03-15 | 2026-03-15 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK11 | 0 | 9232 | 0 | 0 | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-15 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-03-20 | 5 | 2769.6 | 2026-05-29 | 75 | 9232 | 0
EP26030078 | TME-REPSFP-CBI0043D | CBI0043-AG-01_CBI1307-AC-01_D_Rehoming_Bidi_EAS_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | CBI0043D | BOONCHOT BORIWUT | ER | 2026-03-13 | 2026-03-13 | 2026-03-13 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK11 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-13 | 2026-04-03 | - | 760.8 | 480 | HUAWEI |  |  |  | 0 | 21 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 21 | 0 |  |  | 3043.2 | 760.8
EP26030079 | TME-REPSFP-PCR0012 | PCR0012-AC-01-PRI0050-AC-02_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | PCR0012 | BOONCHOT BORIWUT | ER | 2026-03-12 | 2026-03-12 | 2026-03-12 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK11 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-03-12 | 2026-03-16 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 4 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 22 | 0 |  |  | 3043.2 | 760.8
EP26030080 | TME-REPSFP-PRI0131 | PRI0131-AC-01-PCR0138-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | PRI0131 | BOONCHOT BORIWUT | ER | 2026-03-12 | 2026-03-12 | 2026-03-12 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK11 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-03-12 | 2026-03-16 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 4 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 22 | 0 |  |  | 3043.2 | 760.8
EP26030081 | TME-REPSFP-CBI0587D | CBI0587-AC-01_D_Rehoming_FPT_EAS_R3 | 2050.47 | 2783 | 2026-03-30 | TME | REPSFP | CBI0587D | BOONCHOT BORIWUT | ER | 2026-03-13 | 2026-03-13 | 2026-03-13 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK11 | 0 | 1413 | 1370 | 0 | 2783 | 0 | - | 2783 | 1800 | 1630 | 1630 | 0 | 0 | Y | Y |  |  | 2783 |  |  |  | 1630 | 1630 | 2500.4 | 1304 | 0 | 2026-03-13 | 2026-04-06 | - | 282.6 | 326 | HUAWEI |  |  |  | 0 | 24 | COMPLETED | IPRAN | 2500.4 | 2026-04-03 | 21 | 0 |  |  | 2500.4 | 282.6
EP26030083 | TME-REPSFP-CBR0886 | CBR0886-AC-01-CBR0300-AC-01_D_Uplink_20G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | CBR0886 | BOONCHOT BORIWUT | ER | 2026-03-16 | 2026-03-16 | 2026-03-16 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-03-16 | 2026-03-18 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 2 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 18 | 0 |  |  | 3043.2 | 760.8
EP26030084 | TME-REPSFP-CBI0016 | CBI0016-AG-01-CBR0266-AC-01_D_Uplink_20G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | CBI0016 | BOONCHOT BORIWUT | ER | 2026-03-12 | 2026-03-12 | 2026-03-12 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK11 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-03-13 | 2026-03-16 | - | 760.8 | 0 | HUAWEI |  |  |  | 1 | 4 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 22 | 0 |  |  | 3043.2 | 760.8
EP26030086 | TME-REPSFP-CBR0266 | CBR0266-AC-01-CBR0886-AC-01_D_Uplink_20G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | CBR0266 | BOONCHOT BORIWUT | ER | 2026-03-16 | 2026-03-16 | 2026-03-16 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 2400 | 0 | 2026-03-16 | 2026-03-18 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 2 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 18 | 0 |  |  | 3043.2 | 760.8
EP26030088 | TME-DIS_ATN-PRI0005 | PRI0005-AC-01_D_Dismantle_EAST_R3 | 1537.29 | 2081 | 2026-03-30 | TME | DIS_ATN | PRI0005 | BOONCHOT BORIWUT | ER | 2026-03-12 | 2026-03-12 | 2026-03-12 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK11 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1350 | 1230 | 1230 | 0 | 0 | Y | Y |  |  | 2081 |  |  |  | 1230 | 1230 | 1687 | 984 | 0 | 2026-03-12 | 2026-04-03 | - | 394 | 246 | HUAWEI |  |  |  | 0 | 22 | COMPLETED | IPRAN | 1687 | 2026-04-03 | 22 | 0 |  |  | 1687 | 394
EP26030018 | HAS-REP_MA-BBRKM | BBRKM_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | BBRKM | NATTAWOOT SUWAN | SR | 2026-03-17 | 2026-03-17 | 2026-03-17 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-17 | 2026-04-03 | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-03-20 | 3 | 2769.6 | 2026-05-29 | 73 | 9232 | 0
EP26030029 | HAS-REP_MA-PKLKG | PKLKG_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | PKLKG | NATTAWOOT SUWAN | SR | 2026-03-17 | 2026-03-17 | 2026-03-17 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-17 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 |  |  | 2769.6 | 2026-05-29 | 73 | 9232 | 0
EP26030021 | HAS-REP_MA-MHNTH | MHNTH_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | MHNTH | NATTAWOOT SUWAN | SR | 2026-03-17 | 2026-03-17 | 2026-03-17 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-17 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-04-18 | 32 | 2769.6 | 2026-05-29 | 73 | 9232 | 0
EP26030022 | HAS-REP_MA-NTPAN | NTPAN_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | NTPAN | NATTAWOOT SUWAN | SR | 2026-03-18 | 2026-03-18 | 2026-03-18 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-18 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 |  |  | 2769.6 | 2026-05-29 | 72 | 9232 | 0
EP26030019 | HAS-REP_MA-KTANG | KTANG_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | KTANG | NATTAWOOT SUWAN | SR | 2026-03-18 | 2026-03-18 | 2026-03-18 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-18 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 |  |  | 2769.6 | 2026-05-29 | 72 | 9232 | 0
EP26030020 | HAS-REP_MA-LMYNG | LMYNG_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | LMYNG | NATTAWOOT SUWAN | SR | 2026-03-19 | 2026-03-19 | 2026-03-19 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-19 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 |  |  | 2769.6 | 2026-05-29 | 71 | 9232 | 0
EP26030027 | HAS-REP_MA-TANOD | TANOD_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | TANOD | NATTAWOOT SUWAN | SR | 2026-03-19 | 2026-03-19 | 2026-03-19 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK12 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 | 0 | 2026-03-19 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 |  |  | 2769.6 | 2026-05-29 | 71 | 9232 | 0
EP26030112 | HAE-NEWSITE-CPGCM | CPGCM_2024 Coverage Expansion Ph2_New Site_ER | 21666.04 | 26422 | 2026-03-30 | HAE | NEWSITE | CPGCM | BOONCHOT BORIWUT | ER | 2026-03-16 | 2026-03-19 | 2026-03-19 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | Adisak Chanmao | 26WK12 | 793 | 24043 | 0 | 1586 | 26422 |  |  | 26422 | 16381.64 | 300 | 0 | 300 | [5 empty] | 26422 | [5 empty] | 26422 | 0 | 5284.4 | 2026-03-24 | 2026-03-25 | - | 0 | 300 | HUAWEI |  |  |  | 5 | 6 | COMPLETED | MBB | 19982.8 | 2026-04-03 | 15 | 6439.2 | 2026-04-03 | 15 | 26422 | 0
EP26030082 | TME-DIS_ATN-RYG0777 | RYG0777-AC-01_D_Dismantle_EAST_R3 | 1537.29 | 2081 | 2026-03-30 | TME | DIS_ATN | RYG0777 | BOONCHOT BORIWUT | ER | 2026-03-18 | 2026-03-18 | 2026-03-18 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1350 | 1230 | 1230 | 0 | 0 | Y | Y |  |  | 2081 |  |  |  | 1230 | 1230 | 1687 | 984 | 0 | 2026-03-18 | 2026-04-07 | - | 394 | 246 | HUAWEI |  |  |  | 0 | 20 | COMPLETED | IPRAN | 1687 | 2026-04-03 | 16 | 0 |  |  | 1687 | 394
EP26030085 | TME-REPSFP-CBR0059 | CBR0059-AC-01-CBI0145-AC-01_D_Uplink_20G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | CBR0059 | BOONCHOT BORIWUT | ER | 2026-03-16 | 2026-03-16 | 2026-03-16 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | [8 empty] | 3804 | [5 empty] | 3043.2 | 0 | 0 | 2026-03-16 | 2026-04-10 | - | 760.8 | 0 | HUAWEI |  |  |  | 0 | 25 | COMPLETED | IPRAN | 3043.2 | 2026-04-18 | 33 | 0 |  |  | 3043.2 | 760.8
EP26030087 | TME-REPSFP-CBR0300 | CBR0300-AC-01-CBR0972-AC-02_D_Uplink_20G_EAST_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | CBR0300 | BOONCHOT BORIWUT | ER | - | - |  | นาย ชัชวาล เคราะห์ดี | VD01205 | CANCEL | CANCEL | Adisak Chanmao |  | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 2400 | 0 | 0 | 0 | 0 | - | - | - | - | - | [5 empty] | 0 | 0 | 0 | - | - | - | 0 | 0 | - | [5 empty] | CANCEL | CANCEL | 0 |  |  | 0 |  |  | 0 | 0
EP26030166 | TME-REPSFP-RYG0709 | RYG0709-AC-01_RYG0004-AG-01_D_Rehoming_Bidi_EAS_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | RYG0709 | BOONCHOT BORIWUT | ER | 2026-03-23 | 2026-03-23 | 2026-03-23 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-24 |  | - | 760.8 | 480 | HUAWEI |  |  |  | 1 |  | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 11 | 0 |  |  | 3043.2 | 760.8
EP26030089 | TME-REPSFP-RYG1873D | DN_RYG1873_RYG0004-AC-01_D_Rehoming_Bidi_EAS_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | RYG1873D | BOONCHOT BORIWUT | ER | 2026-03-23 | 2026-03-23 | 2026-03-23 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-24 | 2026-05-06 | - | 760.8 | 480 | HUAWEI |  |  |  | 1 | 44 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 11 | 0 |  |  | 3043.2 | 760.8
EP26030090 | TME-REPSFP-RYG0004D | RYG0004-AC-01_RYG0709-AC-01_D_Rehoming_Bidi_EAS_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | RYG0004D | BOONCHOT BORIWUT | ER | 2026-03-23 | 2026-03-23 | 2026-03-23 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-24 | 2026-05-06 | - | 760.8 | 480 | HUAWEI |  |  |  | 1 | 44 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 11 | 0 |  |  | 3043.2 | 760.8
EP26030091 | TME-REPSFP-RYG1873 | RYG0004-AG-01_DN_RYG1873_D_Rehoming_Bidi_EAS_R3 | 2932.56 | 3804 | 2026-03-30 | TME | REPSFP | RYG1873 | BOONCHOT BORIWUT | ER | 2026-03-23 | 2026-03-23 | 2026-03-23 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-24 | 2026-05-06 | - | 760.8 | 480 | HUAWEI |  |  |  | 1 | 44 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 11 | 0 |  |  | 3043.2 | 760.8
EP26030092 | TME-REPSFP-RYG0004 | RYG0004-AG-01_D_Rehoming_FPT_EAS_R3 | 2050.47 | 2783 | 2026-03-30 | TME | REPSFP | RYG0004 | BOONCHOT BORIWUT | ER | 2026-03-23 | 2026-03-23 | 2026-03-23 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 1413 | 1370 | 0 | 2783 | 0 | - | 2783 | 1800 | 1630 | 1630 | 0 | 0 | Y | Y |  |  | 2783 |  |  |  | 1630 | 1630 | 2500.4 | 1304 | 0 | 2026-03-24 |  | - | 282.6 | 326 | HUAWEI |  |  |  | 1 |  | COMPLETED | IPRAN | 2500.4 | 2026-04-03 | 11 | 0 |  |  | 2500.4 | 282.6
EP26030161 | TME-DIS_ATN-RYG0037 | RYG0037-AC-02_D_Dismantle_BMA_R3 | 1537.29 | 2081 | 2026-03-30 | TME | DIS_ATN | RYG0037 | BOONCHOT BORIWUT | ER | 2026-03-18 | 2026-03-18 | 2026-03-18 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 1861 | 2432 | 1370 | 111 | 5774 | 0 | - | 5774 | 1350 | 3010 | 3010 | 0 | 0 | Y | Y |  |  | 5774 |  |  |  | 3010 | 3010 | 3426.6 | 2408 | 0 | 2026-03-19 | 2026-04-07 | - | 2347.4 | 602 | HUAWEI |  |  |  | 1 | 20 | COMPLETED | IPRAN | 3426.6 | 2026-04-03 | 16 | 0 |  |  | 3426.6 | 2347.4
EP26030162 | TME-REPIPRAN-CBR0972 | CBR0972-AC-02_D_Retain_New_EAST_R3 | 4636.11 | 5972.2 | 2026-03-30 | TME | REPIPRAN | CBR0972 | BOONCHOT BORIWUT | ER | 2026-03-20 | 2026-03-20 | 2026-03-20 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 4370.2 | 1370 | 232 | 5972.2 |  |  | 5972.2 | 3800 | [8 empty] | 5972.2 | [5 empty] | 5098.16 | 0 | 0 | 2026-03-20 | 2026-04-01 | - | 874.04 | 0 | HUAWEI |  |  |  | 0 | 12 | COMPLETED | IPRAN | 5098.16 | 2026-05-08 | 49 | 0 |  |  | 5098.16 | 874.04
EP26030163 | TME-REPSFP-CBR0336 | CBR0336-AC-01_CBR0972-AC-02_D_Flash_Uplink_10G_EAST_R3 | 1466.28 | 1902 | 2026-03-30 | TME | REPSFP | CBR0336 | BOONCHOT BORIWUT | ER | 2026-03-20 | 2026-03-20 | 2026-03-20 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 1902 | 0 | 0 | 1902 |  |  | 1902 | 1200 | [8 empty] | 1902 | [5 empty] | 0 | 0 | 0 | 2026-03-20 | 2026-06-03 | - | 1902 | 0 | HUAWEI |  |  |  | 0 | 75 | COMPLETED | IPRAN | 1521.6 | 2026-06-07 | 79 | 0 |  |  | 1521.6 | 380.4
EP26030164 | TME-REPSFP-CBR0972 | CBR0972-AC-02_CBR0300-AC-01_D_Flash_Uplink_10G_EAST_R3 | 1466.28 | 1902 | 2026-03-30 | TME | REPSFP | CBR0972 | BOONCHOT BORIWUT | ER | 2026-03-20 | 2026-03-20 | 2026-03-20 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK12 | 0 | 1902 | 0 | 0 | 1902 | 0 | - | 1902 | 1200 | 1200 | 1200 | 0 | 0 | Y | Y |  |  | 1902 |  |  |  | 1200 | 1200 | 0 | 960 | 0 | 2026-03-20 | 2026-06-03 | - | 1902 | 240 | HUAWEI |  |  |  | 0 | 75 | COMPLETED | IPRAN | 1521.6 | 2026-06-07 | 79 | 0 |  |  | 1521.6 | 380.4
EP26030025 | HAS-REP_MA-RSDAH | RSDAH_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | RSDAH | NATTAWOOT SUWAN | SR | 2026-03-28 | 2026-03-28 | 2026-03-28 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK13 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 |  | 2026-03-28 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-04-18 | 21 | 2769.6 | 2026-05-29 | 62 | 9232 | 0
EP26030147 | HAS-REP_MA-BKNPU | BKNPU_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | BKNPU | NATTAWOOT SUWAN | SR | 2026-03-27 | 2026-03-27 | 2026-03-27 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK13 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 |  | 2026-03-27 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-04-18 | 22 | 2769.6 | 2026-05-29 | 63 | 9232 | 0
EP26030009 | TME-REPSFP-CBR0941 | CBR0941-AC-01-CBR0919-AC-01_D_Flash_Uplink_10G_EAST_R3 | 2932.56 | 3804 | 2026-03-22 | TME | REPSFP | CBR0941 | BOONCHOT BORIWUT | ER | 2026-03-25 | 2026-03-25 | 2026-03-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-26 | 2026-03-26 | - | 760.8 | 480 | HUAWEI |  |  |  | 1 | 1 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 9 | 0 |  |  | 3043.2 | 760.8
| TME-REPSFP-RYG0668 | RYG0668-AC-01_RYG0083-AC-01_D_Flash_Uplink_10G_EAST_R3 |  |  | 2026-03-27 | TME | REPSFP | RYG0668 | BOONCHOT BORIWUT | ER | 2026-03-25 | 2026-03-25 | 2026-03-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | [8 empty] | 2400 | [14 empty] | 0 | 0 | 0 | 2026-03-25 | 2026-03-26 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 1 | COMPLETED | IPRAN | 0 |  |  | 0 |  |  | 0 | 0
| TME-REPSFP-RYG0669 | RYG0669-AC-01_RYG0083-AC-01_D_Flash_Uplink_10G_EAST_R3 |  |  | 2026-03-28 | TME | REPSFP | RYG0669 | BOONCHOT BORIWUT | ER | 2026-03-25 | 2026-03-25 | 2026-03-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | [8 empty] | 2400 | [14 empty] | 0 | 0 | 0 | 2026-03-25 | 2026-03-26 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 1 | COMPLETED | IPRAN | 0 |  |  | 0 |  |  | 0 | 0
EP26030077 | TME-AGG_Exp-CBI0028 | CBI0028_D_AGG_Exp_EAST_R3 | 3417.82 | 4413 | 2026-03-30 | TME | AGG_Exp | CBI0028 | BOONCHOT BORIWUT | ER | 2026-03-26 | 2026-03-26 | 2026-03-26 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 4413 | 0 | 0 | 4413 |  |  | 4413 | 2800 | [8 empty] | 4413 | [5 empty] | 3530.4 | 0 | 0 | 2026-03-27 | 2026-03-30 | - | 882.6 | 0 | HUAWEI |  |  |  | 1 | 4 | COMPLETED | IPRAN | 3530.4 | 2026-04-03 | 8 | 0 |  |  | 3530.4 | 882.6
EP26030165 | TME-REPSFP-CBI0051 | CBI0018-AG-01_CBI0051-AC-01_D_Rehoming_10G_EAST_R3 | 2880.4 | 3804 | 2026-03-30 | TME | REPSFP | CBI0051 | BOONCHOT BORIWUT | ER | 2026-03-25 | 2026-03-25 | 2026-03-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 3804 | 0 | 0 | 3804 | 0 | - | 3804 | 2400 | 2400 | 2400 | 0 | 0 | Y | Y |  |  | 3804 |  |  |  | 2400 | 2400 | 3043.2 | 1920 | 0 | 2026-03-26 | 2026-05-06 | - | 760.8 | 480 | HUAWEI |  |  |  | 1 | 42 | COMPLETED | IPRAN | 3043.2 | 2026-04-03 | 9 | 0 |  |  | 3043.2 | 760.8
EP26030093 | TME-REPSFP-CBI0242 | CBI0242-AC-01_D_Rehoming_FPT_EAST_R3 | 2050.47 | 2783 | 2026-03-30 | TME | REPSFP | CBI0242 | BOONCHOT BORIWUT | ER | 2026-03-25 | 2026-03-25 | 2026-03-25 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Adisak Chanmao | 26WK13 | 0 | 1413 | 1370 | 0 | 2783 | 0 | - | 2783 | 1800 | 1630 | 1630 | 0 | 0 | Y | Y |  |  | 2783 |  |  |  | 1630 | 1630 | 2500.4 | 1304 | 0 | 2026-03-26 | 2026-04-06 | - | 282.6 | 326 | HUAWEI |  |  |  | 1 | 12 | COMPLETED | IPRAN | 2500.4 | 2026-04-03 | 9 | 0 |  |  | 2500.4 | 282.6
EP26020048 | HAS-REP_MA-KOSYM | KOSYM_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-02-14 | HAS | REP_MA | KOSYM | NATTAWOOT SUWAN | SR | 2026-03-30 | 2026-03-30 | 2026-03-30 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK14 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 |  | 2026-03-30 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-04-18 | 19 | 2769.6 | 2026-05-29 | 60 | 9232 | 0
EP26030028 | HAS-REP_MA-BNTNS | BNTNS_2025_Site Facility_REP_9K_SR | 7847.2 | 9232 | 2026-03-01 | HAS | REP_MA | BNTNS | NATTAWOOT SUWAN | SR | 2026-04-01 | 2026-04-01 | 2026-04-01 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Payon Sapphat | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK14 | - | 9232 | - | - | 9232 | 0 | - | 9232 | 7385.6 | 7385.6 | 7385.6 | 0 | 0 | Y | Y |  |  | 9232 | [5 empty] | 6462.4 | 0 |  | 2026-04-01 |  | - | 2769.6 | 7385.6 | HUAWEI | [7 empty] | 6462.4 | 2026-04-18 | 17 | 2769.6 | 2026-05-29 | 58 | 9232 | 0
EP26030155 | HAS-REP_MA-BWTSE | BWTSE_2025_Site Facility_REP_6K/200_SR | 9882.95 | 11627 | 2026-03-01 | HAS | REP_MA | BWTSE | NATTAWOOT SUWAN | SR | 2026-04-03 | 2026-04-03 | 2026-04-03 | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | VD00989 | ALLY | Palagon Prommueangma | บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | 26WK14 | - | 11627 | - | - | 11627 | 0 | - | 11627 | 9882.95 | 9301.6 | 9301.6 | 0 | 0 | Y | Y |  |  | 11627 | [5 empty] | 8138.9 | 0 |  | 2026-04-03 |  | - | 3488.1 | 9301.6 | HUAWEI | [7 empty] | 8138.9 | 2026-04-24 | 21 | 3488.1 | 2026-05-29 | 56 | 11627 | 0
EP26020081 | HAE-Cap_Q126-TSTMM | TSTMM_2025 Capacity Expansion Ph5_EXP_ER_Add | 13678.42 | 16681 | 2026-03-30 | HAE | Cap_Q126 | TSTMM | BOONCHOT BORIWUT | ER | 2026-03-30 | 2026-03-31 | 2026-03-31 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK14 | 793 | 9146 | 2579 | 4163 | 16681 | 0 | - | 16681 | 10342.22 | 300 | 0 | 300 | 0 | Y |  |  |  | 16681 | [5 empty] | 10073 | 0 | 3336.2 | 2026-04-02 | 2026-04-05 | - | 6608 | 300 | HUAWEI |  |  |  | 2 | 5 | COMPLETED | MBB | 13011.8 | 2026-04-18 | 18 | 761.4 | 2026-05-16 | 46 | 13773.2 | 2907.8
EP26030160 | HAE-Cap_Q226-MWATM | MWATM_2025 Capacity Expansion Ph5_EXP_ER_Add | 9765.38 | 11909 | 2026-03-30 | HAE | Cap_Q226 | MWATM | BOONCHOT BORIWUT | ER | 2026-03-30 | 2026-03-31 | 2026-03-31 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK14 | 793 | 9530 | 0 | 1586 | 11909 | 0 | - | 11909 | 7383.58 | 300 | 0 | 300 | 0 | Y |  |  |  | 11909 | [5 empty] | 11909 | 0 | 2381.8 | 2026-04-04 | 2026-04-07 | - | 0 | 300 | HUAWEI |  |  |  | 4 | 7 | COMPLETED | MBB | 9823.7 | 2026-04-24 | 24 | 2085.3 | 2026-05-16 | 46 | 11909 | 0
EP26020034 | TME-DIS_ATN-CCS0013 | CCS0013-AC-01_D_Dismantle_EAST_R3 | 1687.29 | 2081 | 2026-03-30 | TME | DIS_ATN | CCS0013 | BOONCHOT BORIWUT | ER | 2026-04-01 | 2026-04-01 | 2026-04-01 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK14 | 0 | 1970 | 0 | 111 | 2081 | 0 | - | 2081 | 1500 | [8 empty] | 2081 | [5 empty] | 1687 | 0 | 0 | 2026-04-01 | 2026-04-20 | - | 394 | 0 | HUAWEI |  |  |  | 0 | 19 | COMPLETED | IPRAN | 1687 | 2026-05-08 | 37 | 0 |  |  | 1687 | 394
EP26020040 | HAS-CC_Q126-SMANT | SMANT_2025 Coverage Expansion (Co NT)_New_SR | 19470.1 | 22906 | 2026-02-01 | HAS | CC_Q126 | SMANT | NATTAWOOT SUWAN | SR | 2026-04-09 | 2026-04-16 | 2026-04-16 | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | VD01056 | ALLY | Payon Sapphat | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | 26WK16 | - | 18741 | 2579 | 1586 | 22906 | 0 | - | 22906 | 18324.8 | 18324.8 | 18324.8 | 0 | 0 | Y | Y | [8 empty] | 17283.7 | 0 |  | 2026-04-10 |  | - | -17283.7 | 18324.8 | HUAWEI | [7 empty] | 17283.7 | 2026-04-24 | 8 | 0 |  |  | 17283.7 | 5622.3
EP26040110 | TME-REPIPRAN-TRT0164D | TRT0164_D_Retain_New_EAST_R3 | 1830.96 | 2364 | 2026-04-30 | TME | REPIPRAN | TRT0164D | BOONCHOT BORIWUT | ER | 2026-02-18 | 2026-02-18 | 2026-02-18 | นาย ชัชวาล เคราะห์ดี | VD01205 | SUBCON | Adisak Chanmao | Sermsiri Bampentam | 26WK8 | 0 | 2364 | 0 | 0 | 2364 |  |  | 2364 | 1500 | [14 empty] | 3261.2 | 0 |  | 2026-01-29 | 2026-02-26 | - | -3261.2 | 0 | HUAWEI |  |  |  | 4 | 8 | COMPLETED | IPRAN | 6522.4 | 2026-04-18 | 59 | 0 |  |  | 6522.4 | -4158.4
EP26040118 | HAE-NEWSITE-HMRAM | HMRAM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 17744.8 | 21640 | 2026-04-30 | HAE | NEWSITE | HMRAM | BOONCHOT BORIWUT | ER | 2026-04-22 | 2026-04-27 | 2026-04-27 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK18 | 779 | 19308 | 0 | 1553 | 21640 |  |  | 21640 | 17744.8 | 300 | 0 | 300 | 0 | Y | [9 empty] | 21640 | 0 | 4328 | 2026-04-29 | 2026-05-01 | - | -21640 | 300 | HUAWEI |  |  |  | 2 | 4 | COMPLETED | MBB | 15847.6 | 2026-05-08 | 11 | 5792.4 | 2026-05-22 | 25 | 21640 | 0
EP26040119 | HAE-Cap_Q226-CBTKM | CBTKM_2026 Coverage Expansion Ph1-existing_EXP_ER | 10722.32 | 13076 | 2026-04-30 | HAE | Cap_Q226 | CBTKM | BOONCHOT BORIWUT | ER | 2026-04-23 | 2026-04-24 | 2026-04-24 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | น.ส. หทัยรัตน์ สิงห์แก้ว | 26WK17 | 779 | 10744 | 0 | 1553 | 13076 |  |  | 13076 | 10722.32 | 300 | 0 | 300 | 0 | Y | [9 empty] | 9852.8 | 0 | 2615.2 | 2026-04-25 | 2026-04-26 | - | -9852.8 | 300 | HUAWEI |  |  |  | 1 | 2 | COMPLETED | MBB | 9852.8 | 2026-05-16 | 22 | 3223.2 | 2026-05-29 | 35 | 13076 | 0
27555 | TME-CON_Q125-CBI0922B | RM-CBI0922/B_SWAP_East R3 | 14830.4 | 18252 | 2502 | TME | CON_Q125 | CBI0922B | BOONCHOT BORIWUT | ER | 2026-05-21 | 2026-05-23 | 2026-05-23 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | Adisak Chanmao | 26WK21 | 0 | 13632 | 1230 | 4644 | 19506 |  |  | 19506 | 12093.72 | 0 | [13 empty] | 0 | 0 | 3901.2 | 2026-05-23 |  | - | 0 | 0 | HUAWEI |  |  |  | 0 |  | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 19506
EP26050020 | HAE-NEWSITE-CMPIM | CMPIM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5865.46 | 7153 | 2605 | HAE | NEWSITE | CMPIM | BOONCHOT BORIWUT | ER |  |  | 0 |  |  |  | Adisak Chanmao |  | 0 | 779 | 19308 | 0 | 1553 | 21640 |  |  | 21640 | 13416.8 | [19 empty] | - | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 21640
EP26050021 | HAE-NEWSITE-RGPPP | RGPPP_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | RGPPP | BOONCHOT BORIWUT | ER | 2026-05-24 | 2026-05-25 | 2026-05-25 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 | 1398 | 2026-05-26 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 14 | COMPLETED | MBB | 779 | 2026-06-07 | 13 | 0 |  |  | 779 | 6211
EP26050022 | HAE-NEWSITE-SFTPM | SFTPM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | SFTPM | BOONCHOT BORIWUT | ER | 2026-05-26 | 2026-05-27 | 2026-05-27 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 |  | 2026-05-29 |  | - | 0 | 0 | HUAWEI |  |  |  | 2 |  | COMPLETED | MBB | 779 | 2026-06-07 | 11 | 0 |  |  | 779 | 6211
EP26050023 | HAE-NEWSITE-SSSNM | SSSNM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | SSSNM | BOONCHOT BORIWUT | ER | 2026-05-27 | 2026-05-28 | 2026-05-28 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 | 1398 | 2026-06-03 |  | - | 0 | 0 | HUAWEI |  |  |  | 6 |  | COMPLETED | MBB | 779 | 2026-06-07 | 10 | 0 |  |  | 779 | 6211
EP26050024 | HAE-NEWSITE-PYMRP | PYMRP_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | PYMRP | BOONCHOT BORIWUT | ER | 2026-05-24 | 2026-05-25 | 2026-05-25 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 | 1398 | 2026-06-02 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 8 | 14 | COMPLETED | MBB | 779 | 2026-06-07 | 13 | 0 |  |  | 779 | 6211
EP26050025 | HAE-NEWSITE-SFHSM | SFHSM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | SFHSM | BOONCHOT BORIWUT | ER | 2026-05-26 | 2026-05-27 | 2026-05-27 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 |  | 2026-05-28 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 12 | COMPLETED | MBB | 5592.6 | 2026-06-07 | 11 | 0 |  |  | 5592.6 | 1397.4
EP26050026 | HAE-NEWSITE-SHSSM | SHSSM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | SHSSM | BOONCHOT BORIWUT | ER | 2026-05-25 | 2026-05-26 | 2026-05-26 | INHOUSE_Anat Srianut | - | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 |  | 2026-05-29 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 3 | 13 | COMPLETED | MBB | 4813.6 | 2026-06-07 | 12 | 0 |  |  | 4813.6 | 2176.4
EP26050027 | HAE-NEWSITE-STSGM | STSGM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 5731.8 | 6990 | 2605 | HAE | NEWSITE | STSGM | BOONCHOT BORIWUT | ER | 2026-05-27 | 2026-05-28 | 2026-05-28 | INHOUSE PHET SAITHONG | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [14 empty] | 0 | 0 | 1398 | 2026-05-29 | 2026-06-05 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 8 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 6990
EP26050028 | HAE-NEWSITE-QPHTM | QPHTM_2025 Coverage Expansion Ph1_New Site_Change SFP bidi_ER | 4324.68 | 5274 | 2605 | HAE | NEWSITE | QPHTM | BOONCHOT BORIWUT | ER | 2026-05-25 | 2026-05-26 | 2026-05-26 | INHOUSE Adirek Kong-ang | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 2180 | 0 | 0 | 2959 |  |  | 2959 | 3269.88 | [14 empty] | 0 | 0 | 591.8 | 2026-05-28 | 2026-05-29 | - | 0 | 0 | HUAWEI |  |  |  | 2 | 3 | COMPLETED | MBB | 779 | 2026-06-07 | 12 | 0 |  |  | 779 | 2180
EP26050001 | HAE-NEWSITE-SPRYM | SPRYM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | 17744.8 | 21640 | 2605 | HAE | NEWSITE | SPRYM | BOONCHOT BORIWUT | ER | 2026-05-28 | 2026-05-28 | 2026-05-28 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK22 | 779 | 19308 | 0 | 1553 | 21640 |  |  | 21640 | 13416.8 | [14 empty] | 0 | 0 |  | 2026-05-29 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 11 | COMPLETED | MBB | 15847.6 | 2026-06-07 | 10 | 0 |  |  | 15847.6 | 5792.4
EP26050029 | HAE-Cap_Q226-TUHGM | TUHGM_2026 Capacity Expansion Ph1_EXP_ER | 23808.7 | 29035 | 2605 | HAE | Cap_Q226 | TUHGM | BOONCHOT BORIWUT | ER | 2026-06-04 | 2026-06-08 | 2026-06-08 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK24 | 779 | 24115 | 0 | 4141 | 29035 |  |  | 29035 | 18001.7 | [14 empty] | 0 | 0 |  | 2026-06-10 | 2026-06-11 | - | 0 | 0 | HUAWEI |  |  |  | 2 | 3 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 29035
EP26050030 | HAE-Cap_Q226-NOGKM | NOGKM_2026 Capacity Expansion Ph1_EXP_ER | 15311.04 | 18672 | 2605 | HAE | Cap_Q226 | NOGKM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 13752 | 0 | 4141 | 18672 |  |  | 18672 | 11576.64 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 18672
EP26050031 | HAE-Cap_Q226-NPHWM | NPHWM_2026 Capacity Expansion Ph1_EXP_ER | 13454.56 | 16408 | 2605 | HAE | Cap_Q226 | NPHWM | BOONCHOT BORIWUT | ER | 2026-06-02 | 2026-06-02 | 2026-06-02 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK23 | 779 | 11488 | 0 | 4141 | 16408 |  |  | 16408 | 10172.96 | [14 empty] | 0 | 0 | 4102 | 2026-06-07 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 5 | 6 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 16408
EP26050032 | HAE-Cap_Q226-NSSKM | NSSKM_2026 Capacity Expansion Ph1_EXP_ER | 16854.28 | 20554 | 2605 | HAE | Cap_Q226 | NSSKM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 15634 | 0 | 4141 | 20554 |  |  | 20554 | 12743.48 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 20554
EP26050033 | HAE-Cap_Q226-AGWNM | AGWNM_2026 Capacity Expansion Ph1_EXP_ER | 19037.94 | 23217 | 2605 | HAE | Cap_Q226 | AGWNM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 18297 | 0 | 4141 | 23217 |  |  | 23217 | 14394.54 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 23217
EP26050034 | HAE-Cap_Q226-PDAGM | PDAGM_2026 Capacity Expansion Ph1_EXP_ER | 16823.12 | 20516 | 2605 | HAE | Cap_Q226 | PDAGM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 15596 | 0 | 4141 | 20516 |  |  | 20516 | 12719.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 20516
EP26050035 | HAE-Cap_Q226-BHKJM | BHKJM_2026 Capacity Expansion Ph1_EXP_ER | 17340.54 | 21147 | 2605 | HAE | Cap_Q226 | BHKJM | BOONCHOT BORIWUT | ER | 2026-06-12 | 2026-06-12 | 2026-06-12 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao |  | 26WK24 | 779 | 16227 | 0 | 4141 | 21147 |  |  | 21147 | 13111.14 | [17 empty] | 2026-06-13 | 2026-06-16 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 4 | COMPLETED | MBB | 0 |  |  | 0 |  | -46185 | 0 | 21147
EP26050036 | HAE-Cap_Q226-PGASM | PGASM_2026 Capacity Expansion Ph1_EXP_ER | 17485.68 | 21324 | 2605 | HAE | Cap_Q226 | PGASM | BOONCHOT BORIWUT | ER | 2026-06-03 | 2026-06-04 | 2026-06-04 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Adisak Chanmao | Apichart Kampuang | 26WK23 | 779 | 16404 | 0 | 4141 | 21324 |  |  | 21324 | 13220.88 | [14 empty] | 0 | 0 | 5331 | 2026-06-08 | 2026-06-10 | - | 0 | 0 | HUAWEI |  |  |  | 4 | 6 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 21324
EP26050037 | HAE-Cap_Q226-BZBLM | BZBLM_2026 Capacity Expansion Ph1_EXP_ER | 10310.68 | 12574 | 2605 | HAE | Cap_Q226 | BZBLM | BOONCHOT BORIWUT | ER | 2026-06-12 | 2026-06-12 | 2026-06-12 | INHOUSE PHET SAITHONG | - | INHOUSE | Palagon Prommueangma | Apichart Kampuang | 26WK24 | 779 | 10242 | 0 | 1553 | 12574 |  |  | 12574 | 7795.88 | [17 empty] | 2026-06-12 | 2026-06-16 | - | 0 | 0 | HUAWEI |  |  |  | 0 | 4 | COMPLETED | MBB | 0 |  |  | 0 |  | -46185 | 0 | 12574
EP26050038 | HAE-Cap_Q226-PHIKM | PHIKM_2026 Capacity Expansion Ph1_EXP_ER | 10722.32 | 13076 | 2605 | HAE | Cap_Q226 | PHIKM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 1553 | 13076 |  |  | 13076 | 8107.12 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 13076
EP26050039 | HAE-Cap_Q226-PKFAM | PKFAM_2026 Capacity Expansion Ph1_EXP_ER | 22701.7 | 27685 | 2605 | HAE | Cap_Q226 | PKFAM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 22765 | 0 | 4141 | 27685 |  |  | 27685 | 17164.7 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 27685
EP26050040 | HAE-Cap_Q226-TBSVM | TBSVM_2026 Capacity Expansion Ph1_EXP_ER | 14117.12 | 17216 | 2605 | HAE | Cap_Q226 | TBSVM | BOONCHOT BORIWUT | ER | 2026-06-02 | 2026-06-03 | 2026-06-03 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK23 | 779 | 12296 | 0 | 4141 | 17216 |  |  | 17216 | 10673.92 | [14 empty] | 0 | 0 |  | 2026-06-08 | 2026-06-10 | - | 0 | 0 | HUAWEI |  |  |  | 5 | 7 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 17216
EP26050041 | HAE-Cap_Q226-WAGWM | WAGWM_2026 Capacity Expansion Ph1_EXP_ER | 15066.68 | 18374 | 2605 | HAE | Cap_Q226 | WAGWM | BOONCHOT BORIWUT | ER | 2026-06-02 | 2026-06-03 | 2026-06-03 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK23 | 779 | 13454 | 0 | 4141 | 18374 |  |  | 18374 | 11391.88 | [14 empty] | 0 | 0 |  | 2026-06-04 | 2026-06-05 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 2 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 18374
EP26050042 | HAE-Cap_Q226-WTNLM | WTNLM_2026 Capacity Expansion Ph1_EXP_ER | 10310.68 | 12574 | 2605 | HAE | Cap_Q226 | WTNLM | BOONCHOT BORIWUT | ER | 2026-06-03 | 2026-06-04 | 2026-06-04 | INHOUSE_Anat Srianut | - | SUBCON | Palagon Prommueangma | Apichart Kampuang | 26WK23 | 779 | 10242 | 0 | 1553 | 12574 |  |  | 12574 | 7795.88 | [14 empty] | 0 | 0 |  | 2026-06-08 | 2026-06-10 | - | 0 | 0 | HUAWEI |  |  |  | 4 | 6 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 12574
EP26050043 | HAE-Cap_Q226-NHINM | NHINM_2026 Capacity Expansion Ph1_EXP_ER | 10722.32 | 13076 | 2605 | HAE | Cap_Q226 | NHINM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 1553 | 13076 |  |  | 13076 | 8107.12 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 13076
EP26050044 | HAE-Cap_Q226-NKSOM | NKSOM_2026 Capacity Expansion Ph1_EXP_ER | 12844.48 | 15664 | 2605 | HAE | Cap_Q226 | NKSOM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 4141 | 15664 |  |  | 15664 | 9711.68 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 15664
EP26050045 | HAE-Cap_Q226-SFDCM | SFDCM_2026 Capacity Expansion Ph1_EXP_ER | 10507.48 | 12814 | 2605 | HAE | Cap_Q226 | SFDCM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10482 | 0 | 1553 | 12814 |  |  | 12814 | 7944.68 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 12814
EP26050046 | HAE-Cap_Q226-TMKCM | TMKCM_2026 Capacity Expansion Ph1_EXP_ER | 14404.12 | 17566 | 2605 | HAE | Cap_Q226 | TMKCM | BOONCHOT BORIWUT | ER | 2026-06-06 | 2026-06-08 | 2026-06-08 | INHOUSE_Anat Srianut | - | SUBCON | Palagon Prommueangma | Apichart Kampuang | 26WK24 | 779 | 12646 | 0 | 4141 | 17566 |  |  | 17566 | 10890.92 | [14 empty] | 0 | 0 |  | 2026-06-09 | 2026-06-15 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 7 | COMPLETED | MBB | 0 |  |  | 0 |  |  | 0 | 17566
EP26050047 | HAE-Cap_Q226-HMTFM | HMTFM_2026 Capacity Expansion Ph1_EXP_ER | 24861.58 | 30319 | 2605 | HAE | Cap_Q226 | HMTFM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 25399 | 0 | 4141 | 30319 |  |  | 30319 | 18797.78 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 30319
EP26050048 | HAE-Cap_Q226-MPHIM | MPHIM_2026 Capacity Expansion Ph1_EXP_ER | 10722.32 | 13076 | 2605 | HAE | Cap_Q226 | MPHIM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 1553 | 13076 |  |  | 13076 | 8107.12 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 13076
EP26050049 | HAE-Cap_Q226-KHWKM | KHWKM_2026 Capacity Expansion Ph1_EXP_ER | 11868.68 | 14474 | 2605 | HAE | Cap_Q226 | KHWKM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12142 | 0 | 1553 | 14474 |  |  | 14474 | 8973.88 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14474
EP26050050 | HAE-Cap_Q226-OTSVM | OTSVM_2026 Capacity Expansion Ph1_EXP_ER | 19429.9 | 23695 | 2605 | HAE | Cap_Q226 | OTSVM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 18775 | 0 | 4141 | 23695 |  |  | 23695 | 14690.9 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 23695
EP26050051 | HAE-Cap_Q226-NKMHM | NKMHM_2026 Capacity Expansion Ph1_EXP_ER | 16058.88 | 19584 | 2605 | HAE | Cap_Q226 | NKMHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 14664 | 0 | 4141 | 19584 |  |  | 19584 | 12142.08 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 19584
EP26050052 | HAE-Cap_Q226-KOCNM | KOCNM_2026 Capacity Expansion Ph1_EXP_ER | 15785.82 | 19251 | 2605 | HAE | Cap_Q226 | KOCNM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 14331 | 0 | 4141 | 19251 |  |  | 19251 | 11935.62 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 19251
EP26050053 | HAE-Cap_Q226-KOPOM | KOPOM_2026 Capacity Expansion Ph1_EXP_ER | 12844.48 | 15664 | 2605 | HAE | Cap_Q226 | KOPOM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 4141 | 15664 |  |  | 15664 | 9711.68 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 15664
EP26050054 | HAE-Cap_Q226-WKHYM | WKHYM_2026 Capacity Expansion Ph1_EXP_ER | 16723.9 | 20395 | 2605 | HAE | Cap_Q226 | WKHYM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 15475 | 0 | 4141 | 20395 |  |  | 20395 | 12644.9 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 20395
EP26050055 | HAE-Cap_Q226-MBLBM | MBLBM_2026 Capacity Expansion Ph1_EXP_ER | 15995.74 | 19507 | 2605 | HAE | Cap_Q226 | MBLBM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 14587 | 0 | 4141 | 19507 |  |  | 19507 | 12094.34 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 19507
EP26050056 | HAE-Cap_Q226-WNBGM | WNBGM_2026 Capacity Expansion Ph1_EXP_ER | 16723.9 | 20395 | 2605 | HAE | Cap_Q226 | WNBGM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 15475 | 0 | 4141 | 20395 |  |  | 20395 | 12644.9 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 20395
EP26050057 | HAE-Cap_Q226-CAKCM | CAKCM_2026 Capacity Expansion Ph1_EXP_ER | 17042.06 | 20783 | 2605 | HAE | Cap_Q226 | CAKCM | BOONCHOT BORIWUT | ER | 2026-06-10 | 2026-06-11 | 2026-06-11 | INHOUSE PHET SAITHONG | - | INHOUSE | Palagon Prommueangma | Apichart Kampuang | 26WK24 | 779 | 15863 | 0 | 4141 | 20783 |  |  | 20783 | 12885.46 | [17 empty] | 2026-06-12 | 2026-06-16 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 5 | COMPLETED | MBB | 0 |  | -46184 | 0 |  | -46184 | 0 | 20783
EP26050058 | HAE-Cap_Q226-MHBTM | MHBTM_2026 Capacity Expansion Ph1_EXP_ER | 11868.68 | 14474 | 2605 | HAE | Cap_Q226 | MHBTM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12142 | 0 | 1553 | 14474 |  |  | 14474 | 8973.88 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14474
EP26050059 | HAE-Cap_Q226-MONKM | MONKM_2026 Capacity Expansion Ph1_EXP_ER | 18493.46 | 22553 | 2605 | HAE | Cap_Q226 | MONKM | BOONCHOT BORIWUT | ER | 2026-06-10 | 2026-06-11 | 2026-06-11 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Palagon Prommueangma | Apichart Kampuang | 26WK24 | 779 | 17633 | 0 | 4141 | 22553 |  |  | 22553 | 13982.86 | [17 empty] | 2026-06-13 | 2026-06-16 | - | 0 | 0 | HUAWEI |  |  |  | 2 | 5 | COMPLETED | MBB | 0 |  | -46184 | 0 |  | -46184 | 0 | 22553
EP26050060 | HAE-Cap_Q226-WNIBM | WNIBM_2026 Capacity Expansion Ph1_EXP_ER | 10525.52 | 12836 | 2605 | HAE | Cap_Q226 | WNIBM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10504 | 0 | 1553 | 12836 |  |  | 12836 | 7958.32 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 12836
EP26050061 | HAE-Cap_Q226-CITYM | CITYM_2026 Capacity Expansion Ph1_EXP_ER | 14286.86 | 17423 | 2605 | HAE | Cap_Q226 | CITYM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12503 | 0 | 4141 | 17423 |  |  | 17423 | 10802.26 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 17423
EP26050062 | HAE-Cap_Q226-CNPHM | CNPHM_2026 Capacity Expansion Ph1_EXP_ER | 19501.24 | 23782 | 2605 | HAE | Cap_Q226 | CNPHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 18862 | 0 | 4141 | 23782 |  |  | 23782 | 14744.84 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 23782
EP26050063 | HAE-Cap_Q226-NCHKM | NCHKM_2026 Capacity Expansion Ph1_EXP_ER | 20219.56 | 24658 | 2605 | HAE | Cap_Q226 | NCHKM | BOONCHOT BORIWUT | ER | 2026-06-11 | 2026-06-13 | 2026-06-13 | INHOUSE_Anat Srianut | - | SUBCON | Palagon Prommueangma | Apichart Kampuang | 26WK24 | 779 | 19738 | 0 | 4141 | 24658 |  |  | 24658 | 15287.96 | [19 empty] | - | 0 | 0 | HUAWEI | [5 empty] | COMPLETED | MBB | 0 |  | -46186 | 0 |  | -46186 | 0 | 24658
EP26050064 | HAE-Cap_Q226-NGKTM | NGKTM_2026 Capacity Expansion Ph1_EXP_ER | 17485.68 | 21324 | 2605 | HAE | Cap_Q226 | NGKTM | BOONCHOT BORIWUT | ER | 2026-06-03 | 2026-06-06 | 2026-06-06 | INHOUSE PHET SAITHONG | - | INHOUSE | Palagon Prommueangma | Apichart Kampuang | 26WK23 | 779 | 16404 | 0 | 4141 | 21324 |  |  | 21324 | 13220.88 | [14 empty] | 0 | 0 | 5331 | 2026-06-08 | 2026-06-11 | - | 0 | 0 | HUAWEI |  |  |  | 2 | 5 | COMPLETED | MBB | 0 |  | -46179 | 0 |  |  | 0 | 21324
EP26050065 | HAE-Cap_Q226-BBPNM | BBPNM_2026 Capacity Expansion Ph1_EXP_ER | 10722.32 | 13076 | 2605 | HAE | Cap_Q226 | BBPNM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 1553 | 13076 |  |  | 13076 | 8107.12 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 13076
EP26050066 | HAE-Cap_Q226-BNMFM | BNMFM_2026 Capacity Expansion Ph1_EXP_ER | 14404.12 | 17566 | 2605 | HAE | Cap_Q226 | BNMFM | BOONCHOT BORIWUT | ER | 2026-06-02 | 2026-06-03 | 2026-06-03 | INHOUSE_Anat Srianut | - | SUBCON | Palagon Prommueangma | Apichart Kampuang | 26WK23 | 779 | 12646 | 0 | 4141 | 17566 |  |  | 17566 | 10890.92 | [14 empty] | 0 | 0 |  | 2026-06-04 | 2026-06-08 | - | 0 | 0 | HUAWEI |  |  |  | 1 | 5 | COMPLETED | MBB | 0 |  | -46176 | 0 |  |  | 0 | 17566
EP26050067 | HAE-Cap_Q226-BSWHM | BSWHM_2026 Capacity Expansion Ph1_EXP_ER | 16696.84 | 20362 | 2605 | HAE | Cap_Q226 | BSWHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 15442 | 0 | 4141 | 20362 |  |  | 20362 | 12624.44 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 20362
EP26050068 | HAE-Cap_Q226-NGSUM | NGSUM_2026 Capacity Expansion Ph1_EXP_ER | 21374.12 | 26066 | 2605 | HAE | Cap_Q226 | NGSUM | BOONCHOT BORIWUT | ER |  |  | 0 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Palagon Prommueangma |  | 0 | 779 | 21146 | 0 | 4141 | 26066 |  |  | 26066 | 16160.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 26066
EP26050069 | HAE-Cap_Q226-BTDMM | BTDMM_2026 Capacity Expansion Ph1_EXP_ER | 10722.32 | 13076 | 2605 | HAE | Cap_Q226 | BTDMM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10744 | 0 | 1553 | 13076 |  |  | 13076 | 8107.12 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 13076
EP26050070 | HAE-Cap_Q226-BTWWM | BTWWM_2026 Capacity Expansion Ph1_EXP_ER | 10310.68 | 12574 | 2605 | HAE | Cap_Q226 | BTWWM | BOONCHOT BORIWUT | ER | 2026-06-02 | 2026-06-03 | 2026-06-03 | INHOUSE PHET SAITHONG | - | INHOUSE | Palagon Prommueangma | Apichart Kampuang | 26WK23 | 779 | 10242 | 0 | 1553 | 12574 |  |  | 12574 | 7795.88 | [14 empty] | 0 | 0 | 3143.5 | 2026-06-08 | 2026-06-10 | - | 0 | 0 | HUAWEI |  |  |  | 5 | 7 | COMPLETED | MBB | 0 |  | -46176 | 0 |  |  | 0 | 12574
EP26050071 | HAE-Cap_Q226-CMPHM | CMPHM_2026 Capacity Expansion Ph1_EXP_ER | 17969.48 | 21914 | 2605 | HAE | Cap_Q226 | CMPHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 16994 | 0 | 4141 | 21914 |  |  | 21914 | 13586.68 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 21914
EP26050072 | HAE-Cap_Q226-CTLNM | CTLNM_2026 Capacity Expansion Ph1_EXP_ER | 10507.48 | 12814 | 2605 | HAE | Cap_Q226 | CTLNM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 10482 | 0 | 1553 | 12814 |  |  | 12814 | 7944.68 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 12814
EP26050073 | HAE-Cap_Q226-HCPNM | HCPNM_2026 Capacity Expansion Ph1_EXP_ER | 16820.66 | 20513 | 2605 | HAE | Cap_Q226 | HCPNM | BOONCHOT BORIWUT | ER | 2026-06-12 | 2026-06-13 | 2026-06-13 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao | Apichart Kampuang | 26WK24 | 779 | 15593 | 0 | 4141 | 20513 |  |  | 20513 | 12718.06 | [17 empty] | 2026-06-18 |  | - | 0 | 0 | HUAWEI | [5 empty] | COMPLETED | MBB | 0 |  | -46186 | 0 |  | -46186 | 0 | 20513
EP26050074 | HAE-Cap_Q226-EBSMM | EBSMM_2026 Capacity Expansion Ph1_EXP_ER | 14388.54 | 17547 | 2605 | HAE | Cap_Q226 | EBSMM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12820 | 0 | 3948 | 17547 |  |  | 17547 | 10879.14 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 17547
EP26060014 | HAE-NEWSITE-HBSOM | HBSOM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | HBSOM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060015 | HAE-NEWSITE-FKMCM | FKMCM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | FKMCM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060016 | HAE-NEWSITE-SFWBM | SFWBM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | SFWBM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060017 | HAE-NEWSITE-NNJAM | NNJAM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | NNJAM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060018 | HAE-NEWSITE-NCTBM | NCTBM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | NCTBM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060019 | HAE-NEWSITE-SNOTM | SNOTM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | SNOTM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060020 | HAE-NEWSITE-HBSEM | HBSEM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | HBSEM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060021 | HAE-NEWSITE-FRRBM | FRRBM_2024 Coverage Expansion Ph2_New Site_Remote-BBU_ER | 24188.36 | 29498 | 2606 | HAE | NEWSITE | FRRBM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 12417 | 0 | 1553 | 14749 |  |  | 14749 | 18288.76 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB | 0 |  | 0 | 0 |  | 0 | 0 | 14749
EP26060024 | HAE-Cap_Q226-CTRGM2 | CTRGM_2025 Coverage Expansion Ph1_New BBU-2nd_ER | 5731.8 | 6990 | 2606 | HAE | NEWSITE | CTRGM2 | BOONCHOT BORIWUT | ER | 2026-06-06 | 2026-06-08 | 2026-06-08 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao |  | 26WK24 | 779 | 4658 | 0 | 1553 | 6990 |  |  | 6990 | 4333.8 | [17 empty] | 2026-06-18 |  | - | 0 | 0 | HUAWEI |  |  |  | 10 | -46181 | COMPLETED | MBB | 0 |  | -46181 | 0 |  | -46181 | 0 | 6990
EP26060023 | HAE-Cap_Q226-CTRGM | CTRGM_2026 Capacity Expansion Ph1_EXP_ER | 14677.18 | 17899 | 2606 | HAE | NEWSITE | CTRGM | BOONCHOT BORIWUT | ER | 2026-05-31 | 2026-06-02 | 2026-06-02 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao |  | 26WK23 | 779 | 12979 | 0 | 4141 | 17899 |  |  | 17899 | 11097.38 | [17 empty] | 2026-06-12 |  | - | 0 | 0 | HUAWEI |  |  |  | 10 | -46175 | COMPLETED | MBB | 0 |  | -46175 | 0 |  | -46175 | 0 | 17899
EP26060085 | HAE-MOD_Q226-BBPNM | BBPNM_2026 Capacity Expansion Modernize_EXP_ER | 12943.7 | 15785 | 2606 | HAE | MOD_Q226 | BBPNM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 9786.7 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060086 | HAE-MOD_Q226-NOGKM | NOGKM_2026 Capacity Expansion Modernize_EXP_ER | 15120.8 | 18440 | 2606 | HAE | MOD_Q226 | NOGKM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 11432.8 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060087 | HAE-MOD_Q226-SPGTM | SPGTM_2026 Capacity Expansion Modernize_EXP_ER | 15423.38 | 18809 | 2606 | HAE | MOD_Q226 | SPGTM | BOONCHOT BORIWUT | ER | 2026-06-18 | 2026-06-18 | 2026-06-18 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao |  | 26WK25 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 11661.58 | [17 empty] | 2026-06-18 |  |  | 0 | 0 | HUAWEI |  |  |  | 0 | -46191 | ON PROCESS | MBB |  |  | -46191 |  |  | -46191
EP26060088 | HAE-MOD_Q226-TBNCM | TBNCM_2026 Capacity Expansion Modernize_EXP_ER | 17343 | 21150 | 2606 | HAE | MOD_Q226 | TBNCM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 13113 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060089 | HAE-MOD_Q226-TBSVM | TBSVM_2026 Capacity Expansion Modernize_EXP_ER | 14404.12 | 17566 | 2606 | HAE | MOD_Q226 | TBSVM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 10890.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060090 | HAE-MOD_Q226-BUNAM | BUNAM_2026 Capacity Expansion Modernize_EXP_ER | 27064.1 | 33005 | 2606 | HAE | MOD_Q226 | BUNAM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 20463.1 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060091 | HAE-MOD_Q226-WNSWM | WNSWM_2026 Capacity Expansion Modernize_EXP_ER | 17270.84 | 21062 | 2606 | HAE | MOD_Q226 | WNSWM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 13058.44 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060092 | HAE-MOD_Q226-HTPGM | HTPGM_2026 Capacity Expansion Modernize_EXP_ER | 14404.12 | 17566 | 2606 | HAE | MOD_Q226 | HTPGM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 10890.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060093 | HAE-MOD_Q226-KOSHM | KOSHM_2026 Capacity Expansion Modernize_EXP_ER | 17333.98 | 21139 | 2606 | HAE | MOD_Q226 | KOSHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 13106.18 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060094 | HAE-MOD_Q226-KSCSM | KSCSM_2026 Capacity Expansion Modernize_EXP_ER | 17343 | 21150 | 2606 | HAE | MOD_Q226 | KSCSM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 13113 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060095 | HAE-MOD_Q226-KYBSM | KYBSM_2026 Capacity Expansion Modernize_EXP_ER | 17828.44 | 21742 | 2606 | HAE | MOD_Q226 | KYBSM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 13480.04 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060096 | HAE-MOD_Q226-NBLEM | NBLEM_2026 Capacity Expansion Modernize_EXP_ER | 20180.2 | 24610 | 2606 | HAE | MOD_Q226 | NBLEM | BOONCHOT BORIWUT | ER | 2026-06-17 | 2026-06-17 | 2026-06-17 | นาย อภิชาติ ฟังสันเทียะ | VD00235 | SUBCON | Adisak Chanmao |  | 26WK25 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 15258.2 | [17 empty] | 2026-06-17 |  |  | 0 | 0 | HUAWEI |  |  |  | 0 | -46190 | ON PROCESS | MBB |  |  | -46190 |  |  | -46190
EP26060097 | HAE-MOD_Q226-NVOTM | NVOTM_2026 Capacity Expansion Modernize_EXP_ER | 20272.86 | 24723 | 2606 | HAE | MOD_Q226 | NVOTM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 15328.26 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060098 | HAE-MOD_Q226-OTCPM | OTCPM_2026 Capacity Expansion Modernize_EXP_ER | 17996.54 | 21947 | 2606 | HAE | MOD_Q226 | OTCPM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 13607.14 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060099 | HAE-MOD_Q226-PARHM | PARHM_2026 Capacity Expansion Modernize_EXP_ER | 14404.12 | 17566 | 2606 | HAE | MOD_Q226 | PARHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 10890.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060100 | HAE-MOD_Q226-BZBLM | BZBLM_2026 Capacity Expansion Modernize_EXP_ER | 21948.12 | 26766 | 2606 | HAE | MOD_Q226 | BZBLM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 16594.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060101 | HAE-MOD_Q226-PLOCM | PLOCM_2026 Capacity Expansion Modernize_EXP_ER | 16368.02 | 19961 | 2606 | HAE | MOD_Q226 | PLOCM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 12375.82 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060102 | HAE-MOD_Q226-PPKSM | PPKSM_2026 Capacity Expansion Modernize_EXP_ER | 14404.12 | 17566 | 2606 | HAE | MOD_Q226 | PPKSM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 10890.92 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060103 | HAE-MOD_Q226-CITYM | CITYM_2026 Capacity Expansion Modernize_EXP_ER | 14413.14 | 17577 | 2606 | HAE | MOD_Q226 | CITYM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 779 | 779 | 779 | 3116 |  |  | 3116 | 10897.74 | [17 empty] | 2026-06-18 |  |  | 0 | 0 | HUAWEI |  |  |  | 46191 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
EP26060104 | HAE-MOD_Q226-SEAHM | SEAHM_2026 Capacity Expansion Modernize_EXP_ER | 17343 | 21150 | 2606 | HAE | MOD_Q226 | SEAHM | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 779 | 16230 | 0 | 4141 | 21150 |  |  | 21150 | 13113 | [20 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
| TME-FRAN2026-RYG0757 | RYG0757_Flash_RAN_EAS R3 |  |  |  | TME | FRAN2026 | RYG0757 | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 0 | 26134 | 0 | 4729 | 30863 |  |  | 30863 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
| TME-FBAT2026-RYG0757 | RYG0757_Flash_Battery_EAS R3 |  |  |  | TME | FBAT2026 | RYG0757 | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 0 | 5107 | 0 | 0 | 5107 |  |  | 5107 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | BATERRY |  |  | 0 |  |  | 0
| TME-FRAN2026-RYG0654 | RYG0654_Flash_RAN_EAS R3 |  |  |  | TME | FRAN2026 | RYG0654 | BOONCHOT BORIWUT | ER | 2026-06-17 | 2026-06-19 | 2026-06-19 | INHOUSE WACHIRA SAOWARO | - | INHOUSE | Palagon Prommueangma |  | 26WK25 | 0 | 21531 | 0 | 4729 | 26260 |  |  | 26260 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | -46192 | -46192 | ON PROCESS | MBB |  |  | -46192 |  |  | -46192
| TME-FRAN2026-RYG4003 | RYG4003_Flash_RAN_EAS R3 |  |  |  | TME | FRAN2026 | RYG4003 | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 0 | 21242 | 0 | 4729 | 25971 |  |  | 25971 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
| TME-FRAN2026-RYG0571 | RYG0571_Flash_RAN_EAS R3 |  |  |  | TME | FRAN2026 | RYG0571 | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 0 | 3474 | 0 | 0 | 3474 |  |  | 3474 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
| TME-FRAN2026-RYG0627 | RYG0627_Flash_RAN_EAS R3 |  |  |  | TME | FRAN2026 | RYG0627 | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 0 | 3474 | 0 | 0 | 3474 |  |  | 3474 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0 |  |  | 0
| TME-FRAN2026-CBR8841 | CBR8841_Flash_RAN_EAS R3 |  |  |  | TME | FRAN2026 | CBR8841 | BOONCHOT BORIWUT | ER |  |  | 0 | [5 empty] | 0 | 0 | 5592 | 0 | 0 | 5592 |  |  | 5592 | [21 empty] | 0 | 0 | HUAWEI |  |  |  | 0 | 0 | ON PROCESS | MBB |  |  | 0
Formulas:
MONTH = [PM]
PM = IF([PM]<>0,"26WK"&WEEKNUM([PM],2),)
PM = XLOOKUP([PM],'[1]Estimate Plan_export'!$C:$C,'[1]Estimate Plan_export'!$U:$U,)
Note on Z15: Windows 11: Supply and installation of Single antenna mounting and accessory-AIS =1 set
Note on Z16: Windows 11: Install/dismatle Power box without Cables =2 pcs
Note on Z40: Windows 11: Install/dismatle Power box without Cables =2 pcs
Note on Z53: Windows 11: Install Passive unit = 4 Set
Note on Z74: Windows 11: Install Passive unit = 4 Set
Note on Z105: Windows 11: Install Passive unit = 4 Set

## OVERALL PIVOT
1.GRAPH OVERALL INSTALLTION BY WORK ORDER NUMBER
Period WON | (Multiple Items)
Count of On-Service | Column Labels
Row Labels | BOONCHOT BORIWUT | KHATHAHAT SITTHIHONG | NATTAWOOT SUWAN | Grand Total
Jan | 21 |  | 13 | 34
Feb | 67 | 10 | 16 | 93
Mar | 30 | 3 | 17 | 50
Apr | 3 |  | 3 | 6
Grand Total | 121 | 13 | 49 | 183
2.GRAPH OVERALL INSTALLTION BY ESTIMATE FINAL INCOME
Period WON | (Multiple Items)
Sum of ESTIMATE FINAL INCOME | Column Labels
Row Labels | BOONCHOT BORIWUT | KHATHAHAT SITTHIHONG | NATTAWOOT SUWAN | Grand Total
Jan | 407736 |  | 289741 | 697477
Feb | 556231.2 | 45511 | 172739 | 774481.2
Mar | 145155.2 | 6243 | 182856 | 334254.2
Apr | 36797 |  | 43765 | 80562
Grand Total | 1145919.4 | 51754 | 689101 | 1886774.4
3.GRAPH RANKING ESTIMATE FINAL INCOME PER PROJECT
Period WON | (Multiple Items)
Sum of ESTIMATE FINAL INCOME | Column Labels
| Jan | Feb | Mar | Apr | Grand Total
Row Labels
HAE | 391944 | 438761 | 55012 | 34716 | 920433
HAS | 289741 | 172739 | 182856 | 43765 | 689101
TME | 15792 | 117470.2 | 90143.2 | 2081 | 225486.4
HAB |  | 45511 | 6243 |  | 51754
TRS |  | 0 |  |  | 0
TRE |  | 0 |  |  | 0
Grand Total | 697477 | 774481.2 | 334254.2 | 80562 | 1886774.4
4.GRAPH RANKING ESTIMATE FINAL INCOME PER CUSTOMER
Period WON | (Multiple Items)
MONTH | (Multiple Items)
Row Labels | Sum of ESTIMATE FINAL INCOME | Sum of DLPRPO
HUAWEI | 1886774.4 | 856814.52
TRUE | 0 | 0
Grand Total | 1886774.4 | 856814.52

## OVERALL CHART
1.GRAPH OVERALL INSTALLTION BY WORK ORDER NUMBER
2.GRAPH OVERALL INSTALLTION BY ESTIMATE FINAL INCOME
3.GRAPH RANKING ESTIMATE FINAL INCOME PER PROJECT
4.GRAPH RANKING ESTIMATE FINAL INCOME PER CUSTOMER
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## PM PIVOT (hidden)
1.GRAPH OVERALL ESTIMATE FINAL INCOME by Month (ภาพรวมรายได้ต่อเดือนราย PM)
Period WON | (Multiple Items)
Sum of ESTIMATE FINAL INCOME | Column Labels
Row Labels | BOONCHOT BORIWUT | KHATHAHAT SITTHIHONG | NATTAWOOT SUWAN | Grand Total
Jan | 407736 |  | 289741 | 697477
Feb | 556231.2 | 45511 | 172739 | 774481.2
Mar | 145155.2 | 6243 | 182856 | 334254.2
Apr | 36797 |  | 43765 | 80562
Grand Total | 1145919.4 | 51754 | 689101 | 1886774.4
2.GRAPH COMPARE ESTIMATE FINAL INCOME vs SO SAP (INVOICE/IA/GR) (เปรียบเทียบยอดรายได้กับการเก็บรายได้ต่อเดือนราย PM)
Period WON | (Multiple Items)
Column Labels
| BOONCHOT BORIWUT |  | KHATHAHAT SITTHIHONG |  | NATTAWOOT SUWAN |  | Total Sum of ESTIMATE FINAL INCOME | Total Sum of SO SAP
Row Labels | Sum of ESTIMATE FINAL INCOME | Sum of SO SAP | Sum of ESTIMATE FINAL INCOME | Sum of SO SAP | Sum of ESTIMATE FINAL INCOME | Sum of SO SAP
Jan | 407736 | 249340.5 |  |  | 289741 | 160760.3 | 697477 | 410100.8
Feb | 556231.2 | 31355.6 | 45511 | 0 | 172739 | 46202.8 | 774481.2 | 77558.4
Mar | 145155.2 |  | 6243 |  | 182856 |  | 334254.2
Apr | 36797 |  |  |  | 43765 |  | 80562
Grand Total | 1145919.4 | 280696.1 | 51754 | 0 | 689101 | 206963.1 | 1886774.4 | 487659.2
3.GRAPH COMPARE WORK ORDER NUMBER VS DL PRPO ISSUED (เปรียบเทียบจำนวนงานที่แล้วเสร็จกับจำนวนงานที่มีการจัดทำ Direct Labor)
Period WON | (Multiple Items)
Column Labels
| BOONCHOT BORIWUT |  | KHATHAHAT SITTHIHONG |  | NATTAWOOT SUWAN |  | Total Count of On-Service | Total Count of PR END Y/N
Row Labels | Count of On-Service | Count of PR END Y/N | Count of On-Service | Count of PR END Y/N | Count of On-Service | Count of PR END Y/N
Jan | 21 | 21 |  |  | 13 | 13 | 34 | 34
Feb | 67 | 65 | 10 | 7 | 16 | 15 | 93 | 87
Mar | 30 | 21 | 3 | 3 | 17 | 17 | 50 | 41
Apr | 3 |  |  |  | 3 | 3 | 6 | 3
Grand Total | 121 | 107 | 13 | 10 | 49 | 48 | 183 | 165
4.GRAPH COMPARE ESTIMATE FINAL INCOME vs AMOUNT DL PRPO (เปรียบเทียบรายได้ของงานที่แล้วเสร็จกับต้นทุนของงานที่มีการจัดทำ Direct Labor)
Period WON | (Multiple Items)
Column Labels
| BOONCHOT BORIWUT |  | KHATHAHAT SITTHIHONG |  | NATTAWOOT SUWAN |  | Total Sum of ESTIMATE FINAL INCOME | Total Sum of DLPRPO
Row Labels | Sum of ESTIMATE FINAL INCOME | Sum of DLPRPO | Sum of ESTIMATE FINAL INCOME | Sum of DLPRPO | Sum of ESTIMATE FINAL INCOME | Sum of DLPRPO
Jan | 407736 | 92195 |  |  | 289741 | 229676.8 | 697477 | 321871.8
Feb | 556231.2 | 146583.12 | 45511 | 18299 | 172739 | 137344.8 | 774481.2 | 302226.92
Mar | 145155.2 | 46460 | 6243 | 4359 | 182856 | 146284.8 | 334254.2 | 197103.8
Apr | 36797 | 600 |  |  | 43765 | 35012 | 80562 | 35612
Grand Total | 1145919.4 | 285838.12 | 51754 | 22658 | 689101 | 548318.4 | 1886774.4 | 856814.52
5.GRAPH EFFICIENCY of TYPE SUB per Month (ประสิทธิภาพของงานที่แล้วเสร็จเปรียบเทียบตามชนิดของ SUBCON)
Period WON | (Multiple Items)
Count of On-Service | Column Labels
| BOONCHOT BORIWUT |  | BOONCHOT BORIWUT Total | KHATHAHAT SITTHIHONG |  | KHATHAHAT SITTHIHONG Total | NATTAWOOT SUWAN | NATTAWOOT SUWAN Total | Grand Total
Row Labels | INHOUSE | SUBCON |  | ALLY | INHOUSE |  | ALLY
Jan | 9 | 12 | 21 |  |  |  | 13 | 13 | 34
Feb | 17 | 50 | 67 | 9 | 1 | 10 | 16 | 16 | 93
Mar | 3 | 27 | 30 | 3 |  | 3 | 17 | 17 | 50
Apr | 2 | 1 | 3 |  |  |  | 3 | 3 | 6
Grand Total | 31 | 90 | 121 | 12 | 1 | 13 | 49 | 49 | 183
6.GRAPH ESTIMATE FINAL INCOME of TYPE SUB per Month (ประสิทธิภาพการสร้างรายได้ของงานที่แล้วเสร็จเปรียบเทียบตามชนิดของ SUBCON)
Period WON | (Multiple Items)
Sum of ESTIMATE FINAL INCOME | Column Labels
| BOONCHOT BORIWUT |  | BOONCHOT BORIWUT Total | KHATHAHAT SITTHIHONG |  | KHATHAHAT SITTHIHONG Total | NATTAWOOT SUWAN | NATTAWOOT SUWAN Total | Grand Total
Row Labels | INHOUSE | SUBCON |  | ALLY | INHOUSE |  | ALLY
Jan | 203007 | 204729 | 407736 |  |  |  | 289741 | 289741 | 697477
Feb | 283470 | 272761.2 | 556231.2 | 32809 | 12702 | 45511 | 172739 | 172739 | 774481.2
Mar | 55012 | 90143.2 | 145155.2 | 6243 |  | 6243 | 182856 | 182856 | 334254.2
Apr | 34716 | 2081 | 36797 |  |  |  | 43765 | 43765 | 80562
Grand Total | 576205 | 569714.4 | 1145919.4 | 39052 | 12702 | 51754 | 689101 | 689101 | 1886774.4
7.GRAPH RANKING ESTIMATE FINAL INCOME of INHOUSE per PM (การาร้างรายได้ต่อทีม INHOUSE)
Period WON | (Multiple Items)
Column Labels
| INHOUSE PHET SAITHONG | INHOUSE Adirek Kong-ang | INHOUSE WACHIRA SAOWARO | INHOUSE XAIPHONE KHONESOULIN | Grand Total
Sum of ESTIMATE FINAL INCOME | 273696 | 236101 | 66408 | 12702 | 588907
8.GRAPH RANKING ESTIMATE FINAL INCOME of SUBCON per PM (การาร้างรายได้ต่อทีม SUBCON and ALLY)
Period WON | (Multiple Items)
MONTH | (Multiple Items)
Column Labels
| บริษัท เซาท์เทิร์น เทเลคอม เอ็นจิเนียริ่ง คอร์ปอเรชั่น จำกัด | นาย อภิชาติ ฟังสันเทียะ | บริษัท สไปรท์ เซอร์วิส แอนด์ โซลูชั่น จำกัด | นาย ชัชวาล เคราะห์ดี | บริษัท สุพรรณ เทเลคอม จำกัด | บริษัท ทีเอฟแอล ทีมีส จำกัด | บริษัท บี โอ เอส ซี จำกัด | Grand Total
Sum of ESTIMATE FINAL INCOME | 453729 | 344228 | 235372 | 172318.2 | 53168.2 | 39052 | 0 | 1297867.4

## PM CHART (hidden)
1.GRAPH OVERALL ESTIMATE FINAL INCOME by Month (ภาพรวมรายได้ต่อเดือนราย PM)
2.GRAPH COMPARE ESTIMATE FINAL INCOME vs SO SAP (INVOICE/IA/GR) (เปรียบเทียบยอดรายได้กับการเก็บรายได้ต่อเดือนราย PM)
3.GRAPH COMPARE WORK ORDER NUMBER VS DL PRPO ISSUED (เปรียบเทียบจำนวนงานที่แล้วเสร็จกับจำนวนงานที่มีการจัดทำ Direct Labor)
4.GRAPH COMPARE ESTIMATE FINAL INCOME vs AMOUNT DL PRPO (เปรียบเทียบรายได้ของงานที่แล้วเสร็จกับต้นทุนของงานที่มีการจัดทำ Direct Labor)
5.GRAPH EFFICIENCY of TYPE SUB per Month (ประสิทธิภาพของงานที่แล้วเสร็จเปรียบเทียบตามชนิดของ SUBCON)
6.GRAPH ESTIMATE FINAL INCOME of TYPE SUB per Month (ประสิทธิภาพการสร้างรายได้ของงานที่แล้วเสร็จเปรียบเทียบตามชนิดของ SUBCON)
7.GRAPH RANKING ESTIMATE FINAL INCOME of INHOUSE per PM (การาร้างรายได้ต่อทีม INHOUSE)
8.GRAPH RANKING ESTIMATE FINAL INCOME of SUBCON per PM (การาร้างรายได้ต่อทีม SUBCON and ALLY)
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.